## Slide 1: RFP 26-008: ENGINEERING AND DESIGN SERVICES FOR THE Bradley Road – Hancock to Grinnell IMPROVEMENTS PROJECT
El Paso County Department of Public Works
3275 Akers Drive
Colorado Springs, CO 80922
719-520-6460
Pre-Proposal Meeting January 7, 2026 2:00 PM

## Slide 2: Project Team
Procurement:
  Matthew Marter, Senior Procurement Specialist
      MatthewMarter@elpasoco.com
      719-520-6663
Engineering:
  John Andrews
  Brett Hartzell, P.E.

## Slide 3: Funding Source
State/CDOT – Fuel Impacts Enterprise
El Paso County
El Paso County Oversight
State/CDOT Reporting
No Davis-Bacon Requirements

## Slide 4: Timeline
Activity | Deadline
Pre-Proposal Conference | 2:00 PM, Wednesday, January 7, 2026
Final RFP Questions Due | 10:00 AM, Monday, January 12, 2026
Proposal Due Date | 11:00 AM, Wednesday, January 28, 2026
Proposal Review / Consultant Interviews | January 28th through February 11th, 2026
Issue Notice of Intent to Award | February, 2026
Anticipated Start Date | March, 2026

## Slide 5: Project Location
Bradley Road
- 1.4 mile segment between Hancock Expressway / Main Street and Grinnell Boulevard
- Urban Principal Arterial
- 6 Intersections within segment
- Cantrell Drive, Bradley Lane, Bradley Circle,
Alturas Drive, Marabou Way, Wageman Drive
- El Paso County Right-of-Way

## Slide 6: Project details
Bradley Road Background:
  1.4 mile stretch of Urban Principal Arterial
    Primarily 4 lanes, reduces to 2 for southernmost 1000’
    120’ ROW standard, reduces to 50’ for southernmost section
  6 Total Intersections, all stop controlled
    2 3-Way Intersections: Bradley Circle & Bradley Lane
    4 4-Way Intersections, Wageman & Cantrell lack RT lanes
  Pedestrian/Multimodal infrastructure lacks crossing capabilities throughout the corridor
  Ancillary route for fuel and truck traffic

## Slide 7: PROJECT SCOPE
  Drainage Study and Analysis – Hydrology, MS4 Criteria, Permitting
    FEMA No Rise (2 Lane Segment Floodplain)
  Geotechnical Study and Analysis – Field exploration and Subsurface Investigation (20 Borings anticipated)
  Design Survey – Topographic, Survey Control, Utility locates
  Traffic and Safety Analysis – Traffic/Turning Movement Counts, Intersection Control Evaluation (ICE), Conceptual Lighting
  Property Acquisition – Permission to Enter (PTE), Property Impacts, Acquisitions
  Preliminary and Final Engineering Design
    30% Combined with Alternative Analysis (as applicable)
    60% (FIR) Schedule, Phasing, Erosion Control (ESQCP), Estimates
    Final Design (FOR to BID)

## Slide 8: Project Timeline
Design: March 2026 – December 31, 2027
  2026:
    Survey, Investigations, Studies
    Alternative Analysis
    Preliminary Design
    60% Design
  2027:
    Property Acquisition
    Final Design, Permitting
    Bid Set

## Slide 9: Traffic DETAILS
Crash Data:
  50+ Incidents along corridor since 2018
  0 fatalities
  PPACG Crash Data available
Intersections primary collision points
  Marabou and Wageman have highest occurrences

## Slide 10: Drainage DETAILS
Roadway Drainage:
  Primarily Roadside Ditch
  6 Median inlets
  Primarily outfalls to Fountain Mutual Irrigation Canal No. 4
  Irrigation Canal box culverts present at Marabou and Wageman
FEMA Floodplain
  AE bounds N extents of 2-lane segment, roadway generally contained within 1% Annual Chance

## Slide 11: Project details II
Roadway
  Mixture of existing conditions throughout corridor:
    Cantrell to Alturas: C&G w/ reduced shoulder, striped median
    Alturas through Wageman: Expanded shoulder, C&G median – variable width
    Grinnell Connection: Reduced shoulder, no median
  Posted speed of 40 MPH, intermittent guardrail south of Marabou (abutment with Irrigation Canal)
  Pedestrian features limited to intersections

## Slide 12: Property ACQUISITION/ACCESS
Permission to Enter Property (PTE) will be required prior to investigative work & survey on all private property
Access to all residential and commercial properties to be maintained, some additional coordination required:
  Security Fire Department Station 3
  Widefield School District No. 3
Appraisals not anticipated, consultant shall perform negotiations with all affected property owners.
14 Legal Descriptions & 6 Legal Exhibits anticipated

## Slide 13: Utilities
Expected Conflicts:
  Fountain Mutual Irrigation Company (Canal No. 4)
  El Paso County (Windmill Gulch EDB)
Contactor to coordinate will all other utility companies as necessary
  Potholing will be required, assumption of 40 potholes
  811 coordination required
  SUE Quality Level A expected for Final Design

## Slide 14: General Notes
Design shall be primarily focused on safety improvements and reconstruction of roadway to meet County criteria
  Intersection Improvements
  Corridor Lighting
  Road Widening/Continuity
Phasing and Traffic Control plans will be included in final design, but shall be informational in nature.
Due to nature of FIE funding, Consultant shall pursue a shovel-ready design with potential for design services during construction.

## Slide 15: questions