El Paso County

Contracts and Procurement Division

15 East Vermijo Ave

Colorado Springs, CO 80903

REQUEST FOR PROPOSAL #26-016

COVER SHEET

Release Date						      February 4, 2026

Solicitation Number	RFP-26-016

Solicitation Title	DESIGN OF THE MERIDIAN ROAD / FLOWER ROAD INTERSECTION IMPROVEMENTS

Services to be performed for	El Paso County Department of Public Works – Engineering

Responses will be received until			      2:00 P.M., MST, Wednesday, March 4, 2026

Electronically through the Rocky Mountain E-Purchasing System

For additional information please contact	Matthew Marter

Senior Procurement Specialist

Email: matthewmarter@elpasoco.com

Phone: 719-520-6663

Documents included in this package	Request for Proposal Cover Sheet

Executive Summary

Specifications

Special Terms and Conditions General Terms and Conditions Response Submittal Requirements Attachments

The undersigned hereby affirms that (1) he/she is a duly authorized agent of the Consultant , (2) he/she has read all terms and conditions and technical specifications which were made available in conjunction with this solicitation and fully understands and accepts them unless specific variations have been expressly listed in his/her offer, (3) that the offer is being submitted on behalf of the Consultant in accordance with any terms and conditions set forth in this document, and (4) that the Consultant will accept any awards made to it as a result of the offer submitted herein for a minimum of ninety calendar days following the date of submission. Offers must contain, in blue ink, a manual signature of an authorized agent of the Consultant or a verifiable electronic time and date stamped signature in the space provided on all appropriate signature lines in this solicitation. Typed names as signatures are not allowed.

PRINT OR TYPE YOUR INFORMATION

Company Name:

Address:	City/State/Zip:

Contact Person:	Title:

Email: 	Phone:

Authorized Representative’s Signature: 	Date:

Printed Name: 	Title:

Email:	Phone:

REQUEST FOR PROPOSAL #26-016

EXECUTIVE SUMMARY

OFFICIAL SOLICITATION DOCUMENTS: El Paso County officially distributes solicitation documents through the Rocky Mountain E-Purchasing System and the County’s website. Copies of solicitations obtained from any other source are not considered official copies. Only those Consultants who obtain solicitation documents from the Rocky Mountain E-Purchasing System or El Paso County website will be in receipt of officially posted and relevant information regarding solicitations issued by El Paso County. The County and PPRTA cannot be held responsible for incorrect information, nor can it attest to the accuracy of information found on websites other than the Rocky Mountain E-Purchasing System or the County’s website.

PURPOSE OF SOLICITATION: El Paso County (County) and the Pikes Peak Rural Transportation Authority (PPRTA) is requesting proposals from qualified, experienced, professional Consultants to furnish all services, labor, materials, and equipment necessary for professional services for the Meridian Road/Flower Road Intersection Improvement Project. (“The Project”).

The Project is being funded through the Pikes Peak Rural Transportation Authority (PPRTA).  There will be no Federal or State (CDOT) oversight of the project. There is a 0.0% DBE goal associated with the design of this project. This project is not subject to Davis-Bacon requirements.

There is El Paso County and PPRTA oversight of the Project.

The County of El Paso, in accordance with the provisions of Title VI of the Civil Rights Act of  1964 (78 Stat. 252, 42 US.C. §§ 2000d to 2000d-4) and the Regulations, hereby notifies all proposer that it will affirmatively ensure that any contract entered into pursuant to this solicitation, disadvantaged business enterprises (DBE) will be afforded full and fair opportunity to submit proposals in response to this solicitation and will not be discriminated against on the grounds of race, color, or national origin in consideration for an award.

TERM OF CONTRACT: The awarded contract(s) is anticipated to commence on March 15, 2026, and shall remain in effect through July 31, 2030.

TERM OF CONTRACT – MULTI-YEAR: This is a multi-year (4-year) agreement by where the services of the Consultant shall be in effect March 15, 2026, through July 31, 2030. The initial term of this Agreement shall be in effect approximately March 15, 2026, through December 31, 2026, at which time the County and PPRTA shall have the option to continue the Agreement for four (4) additional one-year terms under the same terms and conditions of the original Agreement upon approval of annual appropriation each year of the contract. Continuation of the Agreement beyond the initial period is a PPRTA and County prerogative and not a right of the Consultant and will be exercised only when such continuation is clearly in the best interest of PPRTA and the County.

NON-APPROPRIATION: Pursuant to C.R.S.§ 29-1-110, as amended, the financial obligations of the County and PPRTA as set forth herein after the current fiscal year are contingent upon funds for the purpose being appropriated, budgeted and otherwise available. The awarded agreement will automatically terminate on January 1st of the first fiscal year for which funds are not appropriated. The County shall give the Consultant written notice of such non- appropriation

SCHEDULE OF ACTIVITIES: The following activities and dates tentatively outline the process to be used to solicit Consultant responses and to review each Consultant Response:

February 4, 2026	Release Request for Proposal

February 11, 2026 @ 2:00 p.m.	RECOMMENDED Pre-Solicitation Meeting

February 16, 2026 @ 10:00 a.m.	Deadline for Submitting Questions

March 4, 2026 @ 2:00 p.m.	Response Submission Deadline

March 2025	Issue Notice of Intent to Award

March 15, 2025 (estimated)	Contract Award

PRE-SOLICITATION MEETING: A pre solicitation meeting will be held as shown above in the Schedule of Activities, at the Charles “Chuck” Brown Transportation Complex located at 3275 Akers Drive, Colorado Springs, CO. A representative of the Consultant is encouraged to attend this meeting in order to become familiar with the Specifications.

EXAMINATION OF SITE AND CONTRACT DOCUMENTS IS RECOMMENDED: The Contractor is advised to

carefully examine the requirements outlined in the Specifications. It is not the intent of the specifications to cover each and every detail. Any problems that may arise must be promptly reported to the County and will be subject to the decision of the County and PPRTA. The submitter is expected to carefully examine the size and scope of the proposed work prior to submitting its submittal. The Submitter certifies that it has examined the location of the proposed Work and is familiar with the specifications and all contract documents related thereto, and the local conditions at the place where the Work may be performed. The Submitter should carefully check all the quantities and understand that the County will not be responsible for any errors or omissions on the part of the Submitter in making their submittal.

RESPONSE TO QUESTIONS: Questions which arise during the Response preparation period regarding issues around this Solicitation, purchasing and/or award should be directed electronically, via the Rocky Mountain E- Purchasing system, to Matthew Marter, Senior Procurement Specialist, Contracts & Procurement Division, El Paso County. The Consultant submitting the question(s) shall be responsible for ensuring that the question(s) is received by the date and time listed above in the Schedule of Activities for submitting the question(s).

ACCESSIBILITY COMPLIANCE:  Should the Consultant provide a service which provides information and communication technology (ICT), the Consultant shall make commercially and technologically reasonable efforts to comply with all applicable provisions of C.R.S. §24-85-101, et seq., and the Accessibility Standards for Individuals with a Disability as established by the Governor’s Office of Information Technology (OIT) pursuant to Section C.R.S. §24-85-103 (2.5). Consultant shall also make commercially and technologically reasonable efforts to comply with all State of Colorado technology standards related to technology accessibility and with Level AA of the most current version of the Web Content Accessibility Guidelines (WCAG), incorporated in the State of Colorado technology standards. The Consultant who provides ICT will also procure and provide an accessibility and compliance report utilizing the current ITIC Voluntary Product Accessibility Template (VPAT 2.5Rev WCAG) and/or manual testing reports from a qualified testing company to demonstrate reasonable efforts to comply with all State of Colorado technology standards.

REQUEST FOR PROPOSAL #26-016

SUMMARY OF WORK / SPECIFICATIONS

El Paso County and PPRTA are soliciting bids from qualified, experienced contractors to provide all labor, materials, and equipment necessary to complete the Design of the Meridian and Flower Road Intersection Improvements Project. The material and labor services to be purchased pursuant to this solicitation are funded by the Pikes Peak Rural Transportation Authority (PPRTA) and El Paso County.

It is expected that the business and their team members have significant experience with this type of work. The successful Consultant shall be considered and shall remain an independent Consultant throughout the term of any contract awarded pursuant to this Solicitation.

The County of El Paso, in accordance with the provisions of Title VI of the Civil Rights Act of 1964 (79 Stat. 252, 42 US.C. §§ 2000d to 2000d-4) and the Regulations, hereby notifies all submitters that it will affirmatively ensure that any contract entered into pursuant to this solicitation, disadvantaged business enterprises (DBE) will be afforded full and fair opportunity to submit bids in response to this solicitation and will not be discriminated against on the grounds of race, color, or national origin in consideration for any award.

The Project is being funded through the following sources: Pikes Peak Rural Transportation Authority (PPRTA) and El Paso County. There will be no Federal or State (CDOT) oversight. El Paso County and PPRTA will have oversight of the project. There is no DBE goal associated with the design of this project.  This project is NOT subject to Davis-Bacon requirement.

The successful Contractor shall be solely responsible for scheduling and coordinating work of the sub-contractors, suppliers, and other individuals or entities performing or furnishing any of the work under direct or indirect contract with the successful Contractor.

The successful Contractor shall provide and assume full responsibility for all services, materials, equipment, and labor necessary for completion of the services outlined in this Solicitation as awarded.

# BACKGROUND / GENERAL INFORMATION

The Meridian Road and Flower Road intersection (the “Intersection”) currently exists with two-way stop-control. The intersection is located approximately 0.25 miles southwest of the Woodmen Road and Meridian Road intersection within the community of Falcon in El Paso County, Colorado. Meridian Road provides access between US24 and Woodmen Road and to the Falcon area. Flower Road is a two-lane Local that connects McLaughlin Road with Meridian Road and enters the large shopping center northwest of the intersection.  Meridian Road is classified as a minor arterial and Flower Road is classified as a local. The Meridian Road and Flower Road intersection (the “Intersection”) currently exists with two-way stop-control. The intersection is located approximately 0.25 miles southwest of the Woodmen Road and Meridian Road intersection within the community of Falcon in El Paso County, Colorado. Meridian Road provides access between US24 and Woodmen Road and to the Falcon area. Flower Road is a two-lane Local that connects McLaughlin Road with Meridian Road and enters the large shopping center northwest of the intersection.  Meridian Road is classified as a minor arterial and Flower Road is classified as a local.

The area surrounding the intersection is generally commercial.  The Walmart Supercenter is located northwest of the intersection. Additional retail and fast-food establishments are located along both sides of Meridian Road. There is a large drainage basin in the northeast corner of the Merdian and Flower intersection.

In summer 2025, Matrix Design Group, Inc. completed an Alternative Analysis to help determine the best intersection improvements to improve left-turn capacity into and out of the Walmart Supercenter while also mitigating traffic delay and traffic crashes in the intersection. Due to limited access out of the shopping center, many motorists exit the shopping center onto Meridian Road at the northern right-in/right-out (RIRO) driveway, south of Woodmen Road. Since many of these motorists want to travel north along Meridian Road to access Woodmen Road and other parts of the Falcon community, a high volume of U-turns has been taking place along southbound Meridian Road at the Flower Road intersection. The median is wide and sight distance is limited for northbound and southbound left-turns/U-turns from Meridian Road. This has caused several traffic crashes including serious injury and fatal crashes. A roundabout or traffic signal were recommended at this intersection in the previous study with the roundabout preferred due to a higher reduction in traffic crashes. The consultant will confirm these results before preparing preliminary and final designs for the selected intersection. Improvements to this intersection will include geometric, plan and profile, surface and drainage improvements.

# SCOPE OF WORK

# Proposed Condition Assumptions: The proposed improvements shall be designed in accordance with the El Paso County and CDOT standards and comply with the Colorado Springs City Traffic Signal Installation and Parts Specification (if applicable). Existing infrastructure may need to be added, replaced, or relocated as needed. Roadways may require modification to the vertical and/or horizontal profiles and appropriate drainage modifications to construct the improvements. Alterations to existing drainage systems and minor ditch grading may be required but should be minimized to the extent possible.

# Improvements shall minimize property impacts and property acquisition to the extent practicable. Acquisition of right-of-way, permanent easements, and temporary easements on behalf of the County, are anticipated but shall be determined during preliminary design.

# Utility impacts are anticipated.  The consultant shall identify all utility impacts and shall minimize utility impacts to the extent practicable.

# TECHNICAL REQUIREMENTS

# These bid specifications incorporate the documents entitled “STANDARD SPECIFICATIONS FOR ROAD AND BRIDGE CONSTRUCTION”, Colorado Department of Transportation, State of Colorado (2023), the “Pikes Peak Region Asphalt Paving Specifications” (version 6, March 28, 2022) and the “El Paso County Engineering Criteria Manual” (October 2020), as if physically attached and bound herein. The bid specification documents also incorporate the document entitled “COLORADO STANDARD PLANS, COLORADO DEPARTMENT OF TRANSPORTATION, M&S STANDARDS PLANS LIST” (July 31, 2019), as if physically attached and bound herein.

# Each Bidder / Consultant shall be responsible for procuring sufficient copies of the “Colorado Department of Transportation STANDARD SPECIFICATIONS”, the “COLORADO STANDARD PLANS - M&S STANDARDS”, and the “EL PASO COUNTY ENGINEERING CRITERIA MANUAL”, for use in proposing and construction of the Project.

# The Colorado Department of Transportation Standard Specifications for Road and Bridge Construction, 2023, controls construction of this Project. The special provisions supplement the Standard Specifications and take precedence over the Standard Specifications and Construction Plans. When specifications or special provisions contain both English units and SI units, the {English} units apply and are the specification requirement. All methods of procedures, materials, control or work, materials, and basis of measurements not herein covered will comply with the Standard Specifications for Road and Bridge Construction, Department of Transportation, State of Colorado, 2023.

# Asphalt materials and activities shall be in accordance with the “Pikes Peak Region Asphalt Paving Specifications” unless otherwise noted in the Project Special Provisions.

# Construction signage shall follow the federal “MANUAL ON UNIFORM TRAFFIC CONTROL DEVICES”, latest edition (MUTCD).

# The El Paso County Engineering Criteria Manual and the Pikes Peak Region Asphalt Paving Specifications can be downloaded from: https://publicworks.elpasoco.com/policies-manuals/.

# AVAILABLE INFORMATION

# Upon request, the following information shall be made available to the Consultant, at no cost, through a License Agreement with El Paso County that will be completed after the Notice to Proceed date.  The County Project Manager will initiate the correspondence with the County’s IT group, and the Consultant shall fill out the application provided.  The Consultant shall assume that it will take about three (3) weeks to receive the information after the application for the License Agreement has been submitted.

# Aerial photography of corridor flown in 2014, 2016, 2018, and 2020; one (1) foot resolution; GeoTIF format.

# Two (2) foot contours suitable for preliminary design phase (verses final design) two (2) foot contours; flown in 2011; ESRI shapefile format AND/OR ESRI elevation grid; 1.4-meter resolution.

# Assessor’s parcel features geospatial dataset with attributes available (beyond schedule number).

# Land Uses using County land use categories for 2005 thru 2030.

# Water features geospatial dataset, including creeks, lakes/reservoirs, and wetlands. Wetlands data has been certified by the United States Fish and Wildlife Service.

# Floodplains.

# Drainage Basin boundaries.

# Soils geospatial dataset originally developed by Natural Resources Conservation Services (NRCS).

# Wildlife habitat or wildlife impact geospatial datasets originally developed by the Colorado Department of Wildlife.

Additionally, the following documents are available on the El Paso County, Colorado website at:

# https://publicworks.elpasoco.com/policies-manuals/ and https://library.municode.com/co/el_paso_county

# El Paso County Engineering Criteria Manual

- El Paso County Drainage Criteria Manual

- El Paso County Major Transportation Corridors Plan (MTCP)

- Urban Drainage Flood Control District’s Hydrology and Hydraulics Design Tools

- Pikes Peak Region Asphalt Paving Specs – Version 6/ March 2022

- El Paso County Engineering Division – Standard Drawings, July 18, 2023

CDOT Manuals, Bulletins and Guidelines can be found on CDOT’s website at:

https://www.codot.gov/business/designsupport

The Colorado Springs City Traffic Signal Installation and Parts Specification can be found at:

https://coloradosprings.gov/document/specifications-1-22-24published.pdf

# DEFINITIONS

# For clarity in the assignment of responsibilities, the following definitions may have been used:

| AASHTO | American Association of State Highway and Transportation Officials |
| --- | --- |
| ACOE/USACE | Army Corps of Engineers (may also be referred to as USACE) |
| BOCC | El Paso County Board of County Commissioners |
| CDOT | Colorado Department of Transportation Region 2 |
| County | El Paso County Department of Public Works |
| DBE | Disadvantaged Business Enterprise |
| EPC | El Paso County, Colorado |
| FEMA | Federal Emergency Management Agency |
| FHWA | Federal Highway Administration |
| State | Colorado Department of Transportation, Region 2 |
| USFWS | United States Fish and Wildlife Service |

# PROJECT MANAGEMENT AND ADMINISTRATION

# This task shall include general administration, coordination, documenting, scheduling, reporting, and related activities for the overall successful completion of the individual projects.

# Project Manager: The Consultant shall identify a project manager for this project who will work directly for and support the County Project Manager (EPC PM) in the management and administration of the project. The Consultant’s project manager shall be responsive daily Monday through Friday to the EPC PM throughout the project. The Consultant shall also identify an assistant project manager capable of filling in for the project manager if the project manager is not available due to travel, illness, or other event that will be longer than one week in length.

# Schedule: The Consultant shall provide, track, and update the project schedule and milestones utilizing critical-path-method project management software. The schedule shall be developed in sufficient detail to track all project tasks reflected in the statement of work submitted in the approved proposal.  Additional tasks and sub-tasks shall also be included in the schedules where appropriate. The EPC PM will review the project schedule and the Consultant will maintain it throughout the project. An updated schedule along with narrative reports detailing progress, key issues, as well as one (1) month “look ahead” of upcoming work efforts on each project location, shall be provided to the EPC PM with the monthly invoice for the project duration.

# Progress Payments: The Consultant shall prepare and submit to the County no more than monthly charges for costs incurred related to the project. To be eligible for payment, billings must be received within 30 days after the period for which payment is requested and final billings on this contract must be received by the County within 30 days after the end of the contract work. An itemized invoice with backup must be submitted to the County via Trimble Unity Construct (“TUC” or “Construct”). Supporting documentation may include timesheets, receipts, subconsultant invoices (with their backup), travel log or other similar documents.

# The County will reimburse the Consultant’s reasonable, allocable, allowable costs of performance of the Work, not exceeding the maximum agreed total amount.  To be eligible for reimbursement, costs by the Consultant shall be in accordance with the terms and conditions of this contract; necessary for the accomplishment of the Work, reasonable in the amount for the goods and services provided, actual net cost to the Consultant, incurred for Work performed after the effective date of this contract and satisfactorily documented.

# Invoices shall include: the contract number, purchase order number, “Pay Request Number”, a description of the services performed, the dates of performance and the amounts, description of reimbursable expenses, a summary of accounting to include: initial contract amount, additional amount(s) added to contract via change order, amount previously billed, amount billed with current invoice, total amount billed to date including current billing and amount remaining in the contract, a status report that briefly summarizes the work completed within the invoiced pay period and anticipated work for the next month, updated schedule, and any other project specific information requested by the County. Invoices shall be signed by the Project Manager prior to submittal to the County.

# If personnel (title and/or name) that is not listed on the contract approved rate sheet is used on the project, the Consultant shall provide a brief introduction of the employee including their Name, Title, billable rate and short description of their previous work, on-going work and/or future work on the project. This information shall be included on the Status Report sheet.

# Project Updates and Presentations: The Consultant shall be prepared to provide periodic project updates ready for publishing to the El Paso County website.  This data shall be provided in an editable format and/or Adobe Acrobat .PDF format and may include aerial photography, AutoCAD/digital planimetric, digital photographs, as well as verbiage. The Consultant shall also be ready to prepare presentation materials including Power Point presentations in accordance with project outreach and communications efforts.

# PROJECT COORDINATION

# The Consultant shall work closely with the EPC PM to identify impacted or interested parties and to develop strategies and action plans for facilitating communications, obtaining information, and coordinating regulatory approvals, utility issues, and property acquisition as required for advancing the project. Coordination with CDOT will be required.

# The Consultant shall contact and coordinate utility locations with all utility providers within the Project area. Continuous coordination with Utility Providers will be required from concept to final design and into construction.

# The Consultant shall take the lead in scheduling and coordinating all meetings necessary to coordinate with the stakeholders, other affected parties, agencies, and utilities. The Consultant shall facilitate these meetings and provide meeting agendas to all participants prior to the meeting. The Consultant shall provide meeting minutes, and track discussion and action items generated by the meeting attendees.  The Consultant shall not schedule or attend meetings with agencies, developers, or other outside parties without the direction and approval of the EPC PM.

# At least bi-weekly progress meetings will be held with the EPC PM and informal progress plans will be provided for discussion. Assume half telecom and half in-person meetings for the duration of the design. Milestone meetings will be required, such as the kickoff meeting with El Paso County (EPC), FIR plan review, ROW plan review (ROWPR) with EPC, and FOR plans and specifications review with EPC. The Consultant shall not proceed with project tasks until approved by the EPC PM.

# Unless otherwise specified in writing, all deliverables shall be submitted to the EPC PM for distribution. The Consultant shall assume that Bluebeam will be used for distribution of pdf documents for review and comment. EPC staff, Consultant and subconsultants as appropriate shall have access to the Bluebeam session(s).

# WORK IN THE RIGHT-OF-WAY PERMITS AND PERMISSION TO ENTER PROPERTY

# El Paso County: The Consultant AND its subconsultant(s) shall obtain Work in the Right of Way (ROW) permit(s) from EPC for all work in the EPC ROW.  This includes, but is not limited to traffic counts, surveying, geotechnical borings, potholing, etc.  EPC work in the Right-of-Way permit fees will be waived. The EPC Work in the ROW permit(s) will require the following as applicable:

# Provide traffic control in accordance with the Manual on Uniform Traffic Control Devices.  A Method of Handling Traffic plan shall be submitted with the Work in the ROW application.

# The Consultant shall have, and will need to provide proof of, the appropriate bond ($20,000) and insurance ($1,000,000) per Section 5.2.7.F of the El Paso County Engineering Criteria Manual ECM. Bonding will be waived in its entirety for all work that does not cause disturbance, i.e., topographic surveying, environmental surveys, traffic counts or similar.

# The EPC Work in the ROW permit application can be found here: https://publicworks.elpasoco.com/forms-applications/

# EPC applications shall be submitted to a central email address: rowpermit@elpasoco.com

# Private Property: Permission to Enter (PTE) forms must be prepared by the Consultant and have signed approval by the property owner’s prior entry. PTE forms will be needed for all work on private property, including, but not limited to survey work, environmental surveys, etc. Multiple work activities may be included on a single PTE form.

# TRAFFIC ANALYSIS UPDATE

# The Alternatives Analysis completed by Matrix Design Group, Inc., included as an attachment, shall be updated using Intersection Control Evaluation (ICE) and Highway Safety Manual crash reduction projections. The consultant shall provide an updated recommendation between a traffic signal and a roundabout with a total benefit/cost ratio accounting for delay improvement, crash reduction, construction and right-of-way costs, and life-cycle costs. The preferred alternative that moves forward to design will be determined from this analysis.

# CONCEPTUAL AND PRELIMINARY ENGINEERING AND ROW PLANS

# This task will expand on the conceptual exhibits/renderings in the Traffic Study and provide conceptual design and preliminary engineering. This task will require assessment of existing available information necessary to determine sight distances, roadway alignments and intersection configurations, lighting, sidewalk and accessibility infrastructure, signing and striping, right-of-way/easements constraints, utility constraints, etc.

# The Consultant shall identify all utilities within the project locations. The Consultant is also expected to identify property ownership and acquisition requirements, necessary utility relocations, and environmental/permitting issues and requirements that will have to be studied and further developed in the final design phase of the project.

# The design (Construction Plans) shall be in accord with the requirements of the latest edition of the American Association of State Highway Transportation Officials (AASHTO) manual, Colorado Department of Transportation (CDOT) Standard Specifications for Road and Bridge Construction (2025), CDOT M&S Standards (2019 and recently updated M&S Standards) or the El Paso County Engineering Criteria Manual, whichever is more strict, and it shall comply with applicable requirements of the Americans With Disabilities Act (ADA), and applicable federal, state, and local regulations and standards.  The Consultant will provide FIR (approximately 30%) level plans and specifications for review and approval prior to proceeding with final design.

# Design Survey: Upon request, the County will make available two (2) foot contours through a License Agreement with El Paso County that may be used to produce digital topography for planning purposes.  The two-foot contours are not sufficient for final design purposes.

# The Consultant shall provide a design survey to establish control, verify existing topography and planimetrics, and identify existing monumentation. The survey coverage should extend to a sufficient distance either side of the existing roadway centerline and along drainage systems to provide adequate data for the proposed roadway and pedestrian improvements. The Consultant shall provide base mapping for 0.1-foot final design drawing accuracy and include a one (1) foot contour interval for topography. The mapping shall utilize ground coordinates and the NAVD88 vertical datum.

# Geotechnical and Subsurface Investigation Report: The Consultant shall identify soil and subsurface information requirements necessary to advance the design. The Consultant shall develop a detailed geotechnical investigation plan including borings and/or test pits for obtaining the information. The Consultant shall prepare a geotechnical and subsurface investigation report that summarizes the findings and establishes the design parameters for the various project elements. Pavement designs shall include composite sections for base course / asphalt along the roadway approaches and base course / concrete within the roundabout. The Consultant may explore Full Depth Reclamation (FDR) if this approach is conducive to the design. Full depth asphalt on native is not acceptable.

# All borings shall be to a minimum depth of 20 feet for roadway and 30 feet for lighting. The Consultant shall assume that borings shall be completed after concept (30%) approval. For estimating purposes, the Consultant shall assume fifteen (15) 20 foot borings and five (5) 30 foot borings will be required. If additional borings are expected, the Consultant shall state the number of additional borings expected and include that cost in their proposal.

# Utility Coordination: The improvements will likely impact existing utilities. All existing utility systems must be considered in the design. The Consultant shall contact and coordinate with utility companies during conceptual design and preliminary engineering. A letter with exhibit notifying utilities of potential impacts and requesting information will be prepared by the Consultant for the EPC PM to send via email to all known providers within each project area. The County will provide the letter template.

# The Construction Plans shall clearly identify the existing location and proposed relocation of the utilities.  The Consultant shall determine utility requirements within the roadway right-of-way and identify any easement or acquisition requirements that may be necessary for relocation. The Consultant may be required to obtain title commitments to assist with property boundaries. The preliminary plans shall be distributed to all affected utility companies for review and comment.  At least one (1) utility coordination meeting will be held, and the Consultant shall implement the results of these investigations and recommendations into the construction and ROW plans.

# Subsurface Utility Engineering (SUE): The Consultant shall provide Subsurface Utility Engineering following the requirements described in Senate Bill 18-167. The Consultant shall provide ASCE 38 Quality Level A (QL A) for areas of known impact and Quality Level B (QL B) or QL C for the remainder of the project area. The location of privately owned and maintained utilities such as sprinkler systems or similar shall be included in the work. The Consultant shall assume that Potholing / Utility Test Holes to establish QL A shall be completed after preliminary plan (60%) approval.

# For estimating purposes, the Consultant shall assume twenty (20) potholes will be required.  If additional potholes are expected, the Consultant shall state the number of additional potholes expected and include that cost in their proposal.

# Utility and SUE plans shall clearly identify the existing location of the subsurface and above ground utilities.

# Environmental Clearances / Permitting: The Consultant shall investigate conditions within the project area and identify any required environmental permitting or environmental clearance requirements necessary to advance the project, e.g. Initial Site Assessment (ISA) checklist, floodplain permitting, wetlands mitigation/permitting, threatened and endangered species, migratory birds, water quality issues, etc. All Work shall be in accordance with the requirements of the current federal and state environmental regulations including the National Environmental Policy Act of 1969 (NEPA), as applicable. The project’s location is not within a floodplain and therefore, a Floodplain Development Permit through the Regional Building Department (RBD) at the Pikes Peak Regional Development Center (PPRD) is not expected to be required. The Consultant shall prepare Permission to Enter (PTE) forms and obtain signed approval by the property owners prior to entering private property.

# Drainage Report: The Consultant shall compile and review drainage reports, drainage basin studies, and FEMA floodplain information for the project area. The Consultant shall provide Project-specific hydrology and hydraulics calculations and complete a project Drainage Report in compliance with the El Paso County Drainage Criteria Manual Volume 1, Chapter 4 – Drainage Report Requirements. The Drainage Report shall include the following components, at a minimum, unless the County specifically waives them:

# Summary of existing drainage system.

# Maps indicating existing drainage system in study area.

# List all criteria followed for hydrology and state whether the existing conditions meet these criteria. If not, state the required modifications so that it can be met.

# List all deviations from the County Engineering Criteria and include supporting information.

- Include an engineer’s certification page with the engineer’s stamp, signature, and date.

# A Drainage Report Checklist can be accessed at the following link: EPC/Checklists/FDR.pdf

# The Consultant shall analyze and address all stormwater requirements to ensure that the Project is compliant with the El Paso County MS4 permit. The analysis and backup documentation shall be presented in a report or memo format and may be incorporated into the Drainage Report. Structures, if required, shall be designed to handle the 100-year storm, per County standards. Water surface profiles for the design storms and flood delineation, including FEMA floodplain, as applicable, shall be evaluated and included with the report.

# Stormwater and Water Quality: The Consultant shall analyze and address all stormwater and water quality requirements to ensure that the Project is compliant with the El Paso County MS4 permit and the Engineering Criteria Manual (appendix I).  The analysis and backup documentation shall be presented in a report format and may be incorporated into the Drainage Report. The Consultant shall fill out EPC Stormwater Checklists to determine water quality applicability and stormwater permitting applicability.  The need/lack of need for the facilitation of water quality requirements shall be completed using the form which can be accessed on the EPC Stormwater page of the Public Works website using the following link: EPC/stormwater/

# The Consultant shall determine any property acquisition requirements that may be required for managing water quality. The Consultant shall implement the results of these investigations and recommendations into the construction and ROW plans.

# Erosion Control / Stormwater Management / Water Quality: A Grading and Erosion Control Plan, detail sheets (as appropriate) and CDOT’s standard SWMP sheets (as appropriate) shall be incorporated into the construction plan set.  Grading and Erosion Control (GEC) and SWMP Checklists can be accessed on the EPC Stormwater page of the Public Works website using the following link: EPC/stormwater/

# Conceptual Property Impacts: The Consultant shall provide a list and exhibit(s) to the EPC PM identifying all properties that are likely to be impacted by the project. The Consultant may obtain TBD title commitments for an approved list of properties. Applicable information will be included in the conceptual design package and preliminary plans. For estimating purposes, the Consultant shall assume that six (6) TBD commitments will be required.

# Conceptual Design Package: The Consultant shall develop/update a conceptual design package that defines the improvements that will be advanced into the preliminary and final design stages and incorporates the findings from the investigations identified in the above items. The conceptual design packages shall include the design criteria, conceptual construction drawings, ROW and easement memo and exhibit(s), cost estimate, and a construction timeline. At a minimum, the conceptual drawings shall include base mapping and plan drawings (scale: 1”=100’) showing existing conditions, proposed improvements, existing utility lines and corridors, existing and proposed ROW and/or easements, environmentally sensitive lands that are affected by the improvements, preliminary vertical alignment information, as well as, typical cross-sections showing road lane widths, shoulders, curb & gutter, sidewalk, slopes, drainage elements and utility corridors, as appropriate. Standard plan sheet size shall be 11”x17”.

# Lighting: The Consultant shall provide a lighting design for the roundabout and approaches. The design shall follow CDOT’s Lighting Design Guidelines found at the link below.

https://www.codot.gov/safety/traffic-safety/assets/documents/cdot-lighting-design-guideline.pdf

# Preliminary pole locations and conduit layouts will be provided to assist with determining geotechnical boring and utility pothole locations.

# Preliminary Construction Documents: The Consultant shall prepare preliminary construction plans to include, at a minimum: roadway plans and profiles, typical roadway sections and details, drainage improvements, lighting (pole and conduit locations), construction and post-construction stormwater quality BMPs, existing and proposed utilities and relocations, existing and proposed ROW and easements. A detailed outline of anticipated project specifications shall be provided based on the preliminary plans.

# Preliminary ROW Plans: Based upon the design and title work, the Consultant shall prepare preliminary right-of-way (ROW) plans describing existing and proposed ROW and non-exclusive permanent and temporary easements on behalf of El Paso County if deemed applicable.  The format shall be similar to that used by the Colorado Department of Transportation. Templates may be found online at: https://www.codot.gov/business/manuals/right-of-way-manual/rowplans-chapter2/templates

# Legals descriptions and sketches shall NOT be written until specifically requested by the EPC PM.

# Staging Plans / Traffic Control: The Consultant shall provide recommendations and prepare preliminary staging plans for the improvements including lane closures, detours, and maintenance of traffic provisions that will be required during each phase of construction. This is a high level analysis and plans will be general.

# Cost Estimate: A preliminary construction cost estimate shall be provided based upon the preliminary construction drawings. The estimate will include all elements that will impact the project, including, but not limited to utility relocations, construction, construction management and contingencies. The CDOT cost data book and/or similar recently bid or constructed projects will be the basis for the unit prices unless more accurate local information is available.

# Construction Timeline: A preliminary construction timeline / estimate of working days shall be provided based upon the preliminary construction drawings.  The timeline will include all elements that will impact the project, including, but not limited to utility relocations, construction, and contingencies.

# Concept/Preliminary Deliverables: All deliverables shall be provided electronically. They should be clearly organized and indexed for easy access and retrieval.

# As final deliverables shall be in compliance with Accessibility Standards for Individuals with a Disability, all conceptual and preliminary deliverables shall be in compliance and proof of compliance must be provided before proceeding with final deliverables. EPC may request justification from the Consultant and/or subconsultants for lack of compliance. Coordination and with EPC staff to verify compliance and/or test the deliverables will be available. See the Executive Summary and General Terms and Conditions for additional information.

# The Consultant shall schedule work efforts and resources to produce the required reports and documents identified for this task immediately following Notice to Proceed. Prior to document submission, the Consultant shall also provide draft and/or progress documents to the County in sufficient time to allow County review and incorporation of comments into the final document submittal.  For scheduling purposes, the Consultant should allow 10 to 15 working days for County and CDOT (as applicable) review, depending on the size and complexity of the report/document submission. Draft and final submissions should be reflected on the project schedule.

# Informal progress plans / specifications / reports (as applicable) shall be provided by the Consultant for discussion at all progress meetings.  Hard copy or electronic format will be dependent upon the type of meeting (i.e., telecom or in-person).

# Conceptual (30%) Deliverables include:

# Utility and Permitting Memorandum.

# Draft Stormwater checklists.

# Environmental Impacts, Clearance Requirements, and Permit Requirements Memorandum.

# Property Impacts Memorandum.

# Preliminary Traffic and Safety Analysis Report.

# Design Criteria & Conceptual Design Drawings (11x17 set).

# FIR plan review meeting with EPC.

# Preliminary (60%) Deliverables include:

# Geotechnical and Subsurface Investigation Report.

# Drainage Report.

# Environmental Reports.

- Updated Stormwater Checklists.

# SUE / Utility Plans (QL A).

# Construction Drawings (11x17).

# Grading and Erosion Control Plan (11x17).

# Traffic Control Plan (11x17).

# Right-of-Way Plans (11x17) (ROWPR with EPC).

# Project Specifications & CDOT Standard Special Provisions Outline.

# Design Cost Estimate and Construction Schedule.

# FOR plan review meeting with EPC.

# Public Meeting: Upon approval of conceptual design and any selected alternatives, the County will schedule a public meeting. The meeting will be located near the project site and scheduled on a weekday evening. The purpose of the meeting will be to inform the public and more specifically the impacted business owners and residents about the project and generally describe the proposed improvements / alternatives. The public meeting will be formal and will include a presentation and a formal Q&A.

# The Consultant shall assume the following effort:

# Up to three members of the Consultant’s team shall attend the meeting (approximately three (3) hours).

# Consultant will provide large exhibits depicting the proposed alternatives / intersection improvements.

Consultant will prepare FAQs and comment cards for attendees.

Informal progress plans / specifications / reports (as applicable) shall be provided by the Consultant for discussion at all progress meetings.  Hard copy or electronic format will be dependent upon the type of meeting (i.e., telecom or in-person).

Conceptual (FIR - 30%) Deliverables include:

- Utility and Permitting Memorandum.

- (3) Draft EPC Stormwater Forms/Checklists.

- Environmental Impacts, Clearance Requirements, and Permit Requirements Memorandum.

- Property Impacts Memorandum.

- Design Criteria & Conceptual Design Drawings (11x17 set).

- FIR plan review meeting with EPC.

Preliminary (60%) Deliverables include:

- Geotechnical and Subsurface Investigation Report.

- Drainage Report.

- Environmental Reports.

- (3) Updated EPC Stormwater Forms/Checklists.

- SUE / Utility Plans (QLA).

- Construction Drawings (11x17).

  - Grading and Erosion Control Plan (11x17).

  - Traffic Control Plan (11x17).

- Right-of-Way Plans (11x17) (ROWPR with EPC).

- Project Specifications & CDOT Standard Special Provisions Outline.

- Design Cost Estimate and Construction Schedule.

- FOR plan review meeting with EPC.

# FINAL ENGINEERING / DESIGN SERVICES

# Based on the preliminary design and contract documents approved by the County, the Consultant shall prepare final designs and construction documents for bidding, in hardcopy and electronic format as required by the County. Prior to commencing final plan production, all salient features of the preliminary plan shall be determined for the roadway and approved by the County.

# A plan submittal shall be made in preparation for the Final Office Review (FOR). The FOR plan (approximately 90%) submittal shall be reviewed and approved by the County prior to final plan production.

# Construction Documents: The Consultant shall prepare final designs and final construction documents for bidding. The construction documents will be finalized following the plan format provided by the County. Standard plan sheet size shall be 11x17. Construction drawings shall be signed and sealed by a Professional Engineer licensed in the State of Colorado. Checklists including all final design elements will be provided under separate cover.

# Production of roadway, plan and profile sheets will be developed on a 1” = 100’ scale horizontal, and 1” = 20’ scale vertical, unless otherwise approved. All data (i.e., construction centerline line and curve data) for construction shall be delineated and labeled on the plan and profile drawings in addition to the horizontal control drawings.  Grading plans, separate from the plan and profile drawings, shall also be produced at a scale no smaller than 1” = 100’ and shall include all drainage related grade information including inverts and top of grade for all existing and proposed drainage structures, channels, etc.  Provide cross sections at minimum 25-foot increments and at helpful locations. Include cut/fill data for each section, either on the cross-section sheets or in a summary report. Special details required for the roadway construction shall be prepared and included in the plan set.  Utility relocations, as well as existing utilities, shall be included and clearly delineated in the plan set.

# The plans shall include Summary of Approximate Quantities (SAQ) and Tabulations of Quantities for the roadway and other items – if required. Tabulations shall be created for the benefit of the Consultant and for appropriate line items only.  The SAQ may serve this purpose for some items.

# Requirements for Construction Phasing, Traffic Control, Signage, and Detour Plans, and for Erosion Control and Stormwater Management Plans are further defined below.

# Construction Phasing / Traffic Control / Detour Plans: The Consultant shall prepare final construction phasing and construction traffic control plans to be incorporated in the construction plan set. The construction traffic control plans will be prepared for the project in specific conformance with the Manual of Uniform Traffic Control Devices (MUTCD). These plans shall clearly delineate detours and traffic control signage for each construction phase. Recommendations for the most cost-effective construction traffic control shall be provided for bidding purposes. Traffic control devices such as cones, barrels, etc will NOT be delineated nor quantified.

# The temporary construction phasing traffic control and signage shall be separate sheets, and each phase of traffic control which is assumed to be in place for more than 48 hours shall be delineated separately within the plans and included within the plan set.  (This plan is not to be confused with the requirement of a method for handling traffic (MHT) which shall be provided by the prime Consultant during construction phases.)

# Permanent Signage and Striping Plan: The Consultant shall prepare final permanent traffic control plans to be incorporated in the construction plan set. The plan will be prepared for the project in conformance with the design criteria and the Manual of Uniform Traffic Control Devices (MUTCD). These plans shall clearly delineate and label signage and pavement markings to include Station/Offset.

# Erosion Control / Stormwater Management / Water Quality: The Consultant shall provide final Grading and Erosion Control Plan, detail sheets (as appropriate) and CDOT standard SWMP sheets for inclusion in the contract documents. The Consultant shall review the original EPC Stormwater Checklists to verify that the original determinations for water quality applicability and stormwater permitting applicability are correct.

# Drainage Report: The Consultant shall provide the Final Drainage Report that supports the final design, includes complete design calculations and incorporates all EPC comments. The report shall be signed and sealed by the Professional Engineer responsible for the report.

# Final Utility Coordination: The FOR plans and specifications shall be distributed to all affected utility companies in the corridor for final review and comment.  If required, a utility coordination meeting will be held prior to advertising for construction.  Comments will be incorporated, as appropriate, in the final bid documents. The Consultant shall coordinate requirements for utilities relocation with the County and Utility Providers.  When relocation locations, costs, agreements, and timing have been finalized and agreed upon by the County and Utility providers, the Consultant shall write a Utility Clearance request letter on the County’s behalf.

# Environmental Clearances / Permitting: The Consultant shall obtain, on behalf of the County, all necessary environmental clearances and permits to advance the project.

# ROW Plans: Based upon the final design, utility coordination, property owner coordination and updated title work, the Consultant shall finalize the right-of-way plans describing existing and proposed ROW and easements. The final ROW plans shall be revised to include all updated information from property acquisition negotiations, as required.

# Legal Descriptions and Sketch Exhibits Preparation: The Consultant shall prepare all legal descriptions and sketch exhibits required for the property acquisition process as specified in the Uniform Act. As applicable, the County will honor existing “prescriptive” ROW per the title commitments, BoCC resolution and/or fence lines, and the exhibits shall reflect this as ROW. The format shall follow CDOT criteria.  Example legal descriptions can be found at: https://www.codot.gov/business/manuals/right-of-way-manual/rowplans-chapter2/cdot-descriptions-1

# Individual sketches shall be prepared for each ROW or permanent easement to be acquired, i.e. not combined on one sketch. Sketches for temporary easements are not required – ROW plan sheets and/or construction plan sheets may be used for this purpose. Upon approval by the County, the legal descriptions shall be signed and sealed by the Professional Land Surveyor (PLS) of record prior to submittal to the property owners. For estimating purposes, the Consultant shall assume that fifteen (15) legal descriptions and ten (10) sketches will be required.

# Property / Appraisal Staking: The Consultant shall provide preliminary survey and temporary staking, as required, for proposed right-of-way, permanent easements, and temporary easements for appraisal/value find, property owner viewing, and/or design accuracy. For estimating purposes, the Consultant shall assume that fifteen (15) parcels will be staked.

# Contract Specifications: The Consultant shall produce Project Specifications in accordance with the Colorado Roadway and Bridge Design Manuals and the Colorado Department of Transportation Standard Specifications for Road and Bridge Construction, supplemented by the El Paso County Engineering Criteria Manual. The Project Specifications will include the technical specifications and CDOT standard special provisions. As required, the Consultant shall prepare supplemental specifications to address project specific construction requirements that vary from or are not addressed in the CDOT Standard Specifications. All applicable inserts for the specifications shall be included in the Plans, Specifications and Estimate (PS&E) submittal/specification set such that the submittal shall be ready for advertisement.

# Final Cost Estimate: A detailed engineer’s estimate of probable construction cost shall be updated based upon the completed and approved final design construction drawings. The estimate will include all construction material items, construction survey, mobilization, signing, construction traffic control, and force account work required. The CDOT cost data book will be the basis for the unit prices unless more accurate local information is available. The estimate shall be signed and sealed by the Professional Engineer responsible for preparing the estimate.

# Construction Schedule: The Consultant shall create a construction schedule and provide the estimated number of working days to complete construction.

# Final Design Deliverables: Prior to final document submission, the Consultant shall also provide draft and/or progress documents to the County in sufficient time to allow County review and incorporation of comments into the final document submittal.  For scheduling purposes, the Consultant should allow 10 to 15 working days for review depending on the size and complexity of the report/document submission. Final submissions should be reflected on the project schedule.

# The Consultant shall comply with the following requirements, as applicable:

# Final deliverables shall be in compliance with Accessibility Standards for Individuals with a Disability, and proof of compliance must be provided. EPC may request justification from the Consultant and/or subconsultants for lack of compliance. Coordination and with EPC staff to verify compliance and/or test the deliverables will be available. See the Executive Summary and General Terms and Conditions for additional information.

# Provide the Plans and Reports to the extent required by the nature of the Work.

# Plans and Reports produced and sealed by a Colorado Registered Professional Engineer to ensure Utility Clearance, Environmental Clearance, and Right-of-Way Clearance.

# Provide final assembly of Plans and Contract Documents.

# Be responsible for the Plans being accurate and complete.

# Make no further changes in the Plans following the award of the construction contract except by agreement in writing between the parties.  The Plans shall be considered final when approved and accepted by the parties hereto.

# Afford the County ample opportunity to review the Plans and make any changes in the Plans as directed.

# Final Design Deliverables (FOR and Bid Set Requirements)

# One (1) electronic copy of all deliverables shall be signed and sealed by a Colorado Registered Professional Engineer or Professional Land Surveyor unless otherwise noted.

# FOR Construction Plans.

# FOR Project Specifications.

# ROW Plans.

# Legal Descriptions and Sketches.

# Final Drainage Report.

# Final Environmental Reports.

# Grading and Erosion Control and Water Quality Plan.

# Stormwater checklists (signed and sealed by PE and signed by EPC PM).

# Final Construction Cost Estimate (.pdf and Excel file).

# Bid Set Construction Plans, Project Specifications and CDOT Standard Special Provisions.

# AutoCAD files (to be provided with advertisement for construction).

# One copy of the Final Plans in a .KMZ format showing all proposed work and right-of-way limits. To have the .KMZ file accurately reflect the plans, an accurate geo-location needs to be embedded in the plan’s CADD file. The .KMZ file should be compatible with Google Earth.

# PROPERTY ACQUISITION SERVICES

# Based on the Right-of-Way plans and construction plans approved by the County, the Consultant shall provide property acquisition services for temporary easements, permanent easements, utility easements, and/or right-of-way.  Any acquisition/relocation activities must comply with all federal and state statutes, regulations, CDOT policies and procedures, 49 CFR Part 24, the government wide Uniform Act regulation, the FHWA Project Development Guide, and CDOT’s Right of Way Operations Manual.

# It is anticipated that five (5) properties (5 owners) will be impacted by the Project, with one being CDOT.

# Title Commitments: The Consultant shall obtain updated TBD title commitments for acquisitions requiring a permanent interest in the property. Updated title commitments will be obtained prior to legal description and conveyance document preparation and/or prior to sending Notice of Intent Letters, as required. Title information shall be distributed to the County, the ROW agent, and the appraiser as applicable. The ROW linework and construction plans will be updated by the County, as required. For estimating purposes, the Consultant shall assume that updated title work for six (6) properties will be required.

# Letters, Memorandum of Agreement (MOA), and Conveyance Document Preparation: The Consultant shall prepare all letters required for the property acquisition process as specified in the Uniform Act.  The Consultant shall prepare the MOA and conveyance documents for recording special warranty deeds, non-exclusive permanent easements, and temporary easements. The format shall follow El Paso County criteria. The County Project Manager and County Attorney shall approve the documents prior to submittal to the property owners. Examples of the acquisition letters, MOAs, and conveyance documents shall be provided to the selected Consultant.

# Appraisals / Valuation: If appraisals are required, the Consultant shall coordinate with an independent Certified General Appraiser for property appraisals. An appraisal will be required if the total acquisition value on a parcel is estimated to exceed $25,000. The appraiser shall be competent to prepare eminent domain appraisals. The appraisals shall be based on fair market values for the immediate area. Waiver valuations or value finds will be allowed for property acquisitions with values estimated to be less than or equal to $25,000. For estimating purposes, the Consultant shall assume that no appraisals are expected.

# Negotiations: The Consultant shall perform all negotiations with affected property owners.  All offers must be approved by the County Project Manager prior to presentation to the property owners.  Minimum offers are as follows:

# Temporary easement(s) only: $500.00

# Permanent easement(s) only or including temporary easement(s): $800.00

# Right-of-Way (fee simple) only or including permanent and/or temporary easement(s): $1,000.00

When offers are accepted, the Consultant shall provide original signed documents (MOA, PE’s and TE’s) to the County PM for approval by the Board of County Commissioners (BoCC). A copy of the signed Special Warranty Deed shall be provided in lieu of the original. If a Statement of Authority or similar is required, it shall be recorded in the office of the El Paso County Clerk and Recorder or otherwise approved as appropriate, prior to submitting the acquisition package to the County PM.  Upon approval by the BoCC, a copy of the recorded MOA and BoCC resolution will be provided to the Consultant for their records. The original PE’s and TE’s will be returned to the Consultant to proceed with closing.

# Closings: The Consultant shall organize acquisition closings with the Title Company, the County, and the affected property owners.

# The Consultant shall ensure that the property owner has paid all prior year(s) taxes and current year prorated taxes prior to, or at closing, for Right-of-Way and/or Permanent Easement acquisitions on behalf of the County.

# The Consultant shall obtain partial lien releases for land encumbrances for all acquisitions that include Right-of-Way. Subordination agreements shall be obtained for Permanent easement(s) only or that also include Temporary easement acquisitions on behalf of the County.

# Coordination with the County Attorney will be required to obtain County signatures on closing documents.

# The Consultant shall provide title insurance for each parcel requiring Right-of-Way and/or permanent easement acquisition on behalf of the County.

# All fees associated with partial releases, subordination agreements, closing costs, and title insurance shall be invoiced through the Consultant for reimbursement by the County.  El Paso County recording fees shall be waived.

# ROW & Easement Status Report: The Consultant shall keep a ROW and easement status report spreadsheet including, but not limited to all pertinent property information, type, area, and status of the acquisition, milestone dates, negotiation details, and next steps with an anticipated timeline.  Anticipated costs for property and other negotiated items shall be included.  An electronic example copy will be provided by the County if requested. The updated report shall be presented to the County Project Manager on a weekly basis, as appropriate. Bi-weekly meetings shall be anticipated.

# Project Files: Files shall be maintained and reviewed for both complete and ongoing activities to ensure the thoroughness of all right-of-way support services being provided.  A complete file containing the original documents for each parcel shall be maintained by the Consultant and a final electronic file shall be submitted to the County upon project completion.

# Accessibility: Documents shall be created in compliance with Accessibility Standards for Individuals with a Disability. EPC may request justification from the Consultant and/or subconsultants for lack of compliance. Coordination and with EPC staff to verify compliance and/or test the deliverables will be available. See the Executive Summary and General Terms and Conditions for additional information.

# SERVICES DURING AND AFTER CONSTRUCTION

# DSDC: For estimating purposes, the Consultant shall assume the following:

# The Project Manager will attend five (5) one hour in-person meetings.

# Ten (10) RFI’s will require responses.

# Five (5) submittals will require review.

# ROW and Easement Monumentation: The Consultant shall provide ROW and permanent easement monumentation after construction is complete.  For estimating purposes, the Consultant shall assume that ten (10) ROW and/or easements will require monumentation.

# EVALUATION CRITERIA

# All proposals deemed acceptable shall be initially rated based upon the submitted requirements. Price is not a factor in the Technical Review scoring process.

# The evaluation committee will score Responses based on the following criteria listed in order of importance:

# Ability of Company’s Key Personnel (35%):

# Summarize/list applicable qualifications, licenses, training and/or certifications of Key Personnel. The County may request proof of the listed training, certifications, and/or licenses prior to performing work.

# Describe/summarize Key Personnel’s Relevant Experience.

# Provide a maximum of five (5) “Example Projects” with similar scopes and magnitudes.

# Resumes for Key Personnel may be included if additional information is deemed necessary.  If included, resumes shall be in an appendix and referenced in the proposal as applicable.

# Provide a list of subconsultants that will be used for the proposed work and describe the scope of work that will be provided by each subconsultant.

# Include proposals from subconsultants that meet the requirements listed above. If no subconsultants will be used, state such.

# Understanding and Approach (35%):

# Understanding of the Project requirements.

# Unique approach to management of the Project (i.e., budget, schedule, other).

# Clearly identify Key Personnel’s roles and responsibilities.

# Provide a timeline/schedule for the Work including key critical path events assuming Notice to Proceed (NTP) will be given as shown on the Timetable.

# Additional elements of interest.

# Company’s Qualifications and Experience (15%):

# Ability to provide professional services.

# Relevant Experience:

# Generally, describe projects scope and services provided. Specifically identify key personnel and/or subconsultants involved in similar projects and their roles and responsibilities.

# Provide a maximum of five (5) “Example Projects” with similar scopes and magnitudes.

# Price will be evaluated after the technical evaluations and scores will contribute to the overall ranking.

# Fee Proposal / Price (15%):

# Reasonable overall hours.

# Reasonable hours for each task and hours reflect the assumptions and clarifications in the proposal.

# Hours reflect lower-level staff performing the majority of the work with upper-level staff in a review role.

# Hours for subconsultants are provided and itemized.

# Rate sheets for Consultant and subconsultant(s) are provided and acceptable.

# Please provide a detailed fee schedule per the instructions on Page 22.

# Upon completion of the initial review of proposals, the committee may contact up to three (3) highest ranked firms and schedule interviews with each.  Based on the County’s initial review of the foregoing, if an Offeror’s score is within five (5) points of the highest ranked firm, the County has the option to schedule interviews with the firm(s). The selection criteria utilized during the interview may differ and may include the following factors:

- Past performance / clarifications of relevant or example projects.

- Willingness to meet the budget requirement.

- Current and projected workload.

- Volume of previously awarded contracts.

- Comfort level with presentation and attitude.

# RESPONSE FORMAT AND REQUIRED DOCUMENTATION

# Failure to respond in the required format or failure to provide required information may deem your submittal non-responsive.

# To facilitate an effective review process, responses must be submitted on 8.5” x 11” paper, with a minimum font of  10,  and  all  pages  should  be  numbered  in  the  following  manner:  page  or pages, with a maximum of fifty (50) pages. All acronyms in the response must be defined.

Attachments/Exhibits included in this solicitation, that require signature and/or are a required document to be returned with your Responses shall be included as an exhibit to your Responses and will not be included in the page limit. Requested items in the appendices will not be included in the page limit. Schedules may be submitted on 11" x 17" sheets and are counted as one page.

Submittals should be prepared simply and economically providing a straightforward, concise description of the Consultant’s ability to perform the requirements of this Solicitation.

ELECTRONIC SUBMISSION OF OFFERS: El Paso County will only accept electronic bid Responses submitted through the Rocky Mountain E-Purchasing system. A Submittal Log will be posted after the County has had an opportunity to review and verify the submittals offered to the County and PPRTA.

The original Offer must be received before the due date and time through an electronic package transmitted through the Rocky Mountain E-Purchasing system. The Consultant is responsible for ensuring its Response is posted by the due date and time outlined in the solicitation document.

If the submittal arrives late, it will not be included in the electronic lockbox.

The Solicitation Opening for RFP-26-016 will take place VIA TELECONFERENCE utilizing the call-in information below:

Participant-guest login:

  - Dial access number: 1-719-520-7660

  - Enter the participant-guest pass code: 51488#

  - Attendee access code: 1234#

Proposers are NOT required to participate. No in-person entry to our building will be permitted.

To enable the County to conduct a uniform review of the information submitted in response to this Solicitation, Consultants must address the following information, numbered to directly correspond with the number of the Table of Contents section of the submitted Response. The County reserves the right to reject submittals that do not follow the required format. Include concise, complete information which will demonstrate that your firm is uniquely qualified to provide the products and services specified in this Solicitation.

ALL signatures on required documents must be in blue ink or a verifiable electronic time and date stamped signature in ONE PDF document. Typed names as signatures are not allowed.

- Provide response without reference to El Paso County logo or company logo in one PDF document.

- Submit response in a tab format that follows a clearly outlined Table of Contents that identifies all material and attachments that comprise your response by section and by page number. I.e. –Required Documentation section, Evaluation Criteria section, etc. as outlined on the Response Submittal Requirements page.

- Cover Letter, one-page limit. Submit a Cover Letter on official business letterhead that:

  - Positively states your willingness to comply with all work requirements and other terms and conditions as specified in this Solicitation.

  - Provides, in brief concise terms, a summation of your submittal and identifies the points that make your firm uniquely qualified for this project.

  - Is signed by an Authorized Representative of your firm who has the authority to commit to the proposed work.

- Provide documentation that satisfies the Required Document Requirements

  - Consultant Information Form

  - Proprietary / Confidential Statement

  - Subcontractor list (if applicable)

  - Exhibit 1 – Exceptions Form

  - Exhibit 2 – Lobbying Certification

  - Exhibit 3 – Non-Collusion Affidavit

  - Exhibit 4 – Minimum Insurance Requirements

  - Completed and signed Cover Sheet

  - Addendum(s) Acknowledgement, if applicable

  - Universal Entity Identifier (UEI) Number

  - Pricing Form

  - Documentation of Meeting Minimum Requirements

  - Work Plan and Schedule - Schedules submitted for this bid shall assume a contract award per the IFB Schedule of Activities.

- Provide documentation that satisfies the criteria to be reviewed.

- Provide the completed and signed Cover Sheet

- Addendum(s) Acknowledgement, if applicable

- Submission Form

- Documentation of Meeting Minimum Requirements

- Universal Entity Identifier (UEI) Number

- Additional Attachments, if applicable

# ATTACHMENTS

- Traffic Impact Study – July 2, 2025

- Vicinity Map

- PPRTA – Special Funding Provisions

REQUEST FOR PROPOSAL #26-016

PRICING FORM

Fee Schedule: SUBMIT IN A SEPERATE SEALED ENVELOPE: The fee schedule shall be provided as a separate document in a sealed envelope, independent of the technical proposal. The fee schedules will not be open until all technical evaluations have been completed and proposals have been ranked.

Please provide a detailed fee schedule similar to the format shown on the fee schedule page that includes the following at minimum:

  - Names of Key Personnel.

  - Attach subconsultant fee schedule(s) in similar format as shown on the fee schedule page.

  - Submit a comprehensive rate sheet – Consultant and subconsultant(s).

  - Hourly rates, unit rates, and markups shall be a fixed rate and not a range.

  - A multiplier on personnel rates for overtime/off-hours work or fieldwork conducted using upgrade levels of personal protection (i.e., Level C, B, or A) will not be considered.

  - Non-labor expenses shall be listed at cost (no loading on non-labor).

  - List any additions in Miscellaneous Expenses – be specific.

REQUEST FOR PROPOSAL #26-016

SPECIAL TERMS AND CONDITIONS

- METHOD OF AWARD BEST EVALUATIVE SCORE BASED ON WRITTEN RESPONSE: It is the intent of the County and PPRTA to award this Solicitation to the Vendor who receives the highest score when the Responses submitted by interested Vendors are reviewed by the County's Response Evaluation Committee. For this Solicitation, the Evaluation Committee will score Responses based on the following criteria listed in no order of importance:

- Ability of Company’s Key Personnel (35%)

- Understanding and Approach (35%)

- Company’s Qualifications and Experience (15%)

- Fee Schedule / Price (15%)

A more detailed description of these criteria can be found on Pages 19-20 of this document.

Evaluation criteria, other than costs, are evaluated first. After rating the written Responses, costs are then considered against trade-offs such as satisfaction of requirements in the Solicitation, qualifications and financial condition of the Consultant, risk, and incentives.

If it is in the best interest of the County and PPRTA, the Evaluation Committee may invite a limited number of Consultants who received the highest scores during the written phase to provide an oral presentation and discussion. The number of Consultants who may be invited to participate in this discussion will be determined by the Evaluation Committee after the written Responses have been scored.

The County and PPRTA reserves the right to conduct negotiations with Consultants and to accept revisions of Responses. During this negotiation period, the County and PPRTA will not disclose any information derived from Responses submitted, or from discussions with other Consultants. Once an award is made, the Solicitation file and the Responses contained therein are in the public record.

- LOCATION OF WORK:  This project is located at the intersection of Woodmoor Drive / Lake Woodmoor Drive in the Monument area. See the Specifications section for the specific project locations.

- POST INTENT TO AWARD MEETING: The Consultant may be required to attend a post intent to award meeting with the County to discuss the terms and conditions of the contract. This meeting will be coordinated by the Contracts and Procurement Division once a Notice of Intent to Award has been issued.

- DEBRIEFING: Offeror(s) not selected for award may request a debriefing on the selection process as well as discussion of the strengths and weaknesses of their firm’s proposal upon the Final Notice of Award being posted on the Rocky Mountain E-Purchasing website.

A debriefing may be scheduled by contacting the Procurement Specialist listed on the Cover Sheet of this Solicitation once the Final Notice of Award has been posted.

- ELIGIBILITY OF CONSULTANTS:   Solicitations will only be considered from firms which are engaged in the business of performing services as described in this Solicitation. The Consultants must be able to produce evidence that they have an established satisfactory record of performance for a reasonable period of time and have sufficient financial support, equipment, and organization to ensure that they can satisfactorily execute the services if awarded a contract. The term equipment and organization as used herein shall be construed to mean a fully equipped and well-established company in line with the best business practices in the industry and as determined by the proper authorities of the County. The County reserves the right, before awarding the contract, to require a Consultant to submit such evidence of its qualifications as it may deem necessary and may consider any evidence available to it (including, but not limited to, the financial, technical, and other qualifications and abilities of the Consultant, including past performance and experience with the County) in making the award in the best interest of the County.

- COMPETENCY OF CONSULTANTS - MINIMUM TWO (2) YEARS OF EXPERIENCE AND OPERATIONAL REQUIREMENTS: Bids will only be considered from Consultants which have been engaged in the business of performing the Work as described in this Solicitation. Consultants must be able to produce evidence that they have an established satisfactory record of performance for a minimum of two (2) years and have sufficient financial support, equipment, and organization to ensure that they can satisfactorily execute the services if awarded a contract. The term 'equipment and organization' as used herein shall be construed to mean a fully equipped and well-established company in line with the best business practices in the industry and as determined by the proper authorities of the County and PPRTA.

The Consultant shall submit, with its bid, such evidence of its qualifications including a maximum of three (3) relevant projects with similar services, timelines and/or magnitudes performed by the Consultant in the last five (5) years and relevant projects with similar services, timelines and/or magnitudes performed by the Consultant’s Project Manager, Superintendent and/or Foreman(s).

The County and PPRTA may consider any evidence available to it (including, but not limited to, the financial, technical, and other qualifications and abilities of the Consultant) in making the award in the best interests of the County.

- QUALIFICATIONS OF CONSULTANT: The County and PPRTA may make such investigations as deemed necessary to determine the ability of the Contractor to perform the work, and the Contractor shall furnish all information and data for this purpose as the County and PPRTA requests. Such information includes but not limited to: current/maximum bonding capabilities, current licensing information, audited financial statements, history of the firm on assessments of liquidated damages, contracts cancelled prior to completion and/or lawsuits and/or pending lawsuits against the firm and/or its principals. The County reserves the right to reject any Response if the evidence submitted by, or investigation of, such Contractor fails to satisfy the County that such Contractor is properly qualified to carry out the obligations of the Solicitation and to complete the work contemplated therein. Conditional Responses will not be accepted.

- PAST PERFORMANCE: The County may review Past Performance with El Paso County, PPRTA, or another entity and/or make such investigations as deemed necessary to determine the ability of the Contractor to perform work outlined in this solicitation. If the County has terminated a contract with the Contractor within the past three (3) years, the Contractor may be asked to furnish information for this investigation as the County requests. Such information includes but not limited to: current/past company references, current licensing information, history of the firm on assessments of liquidated damages, contracts cancelled prior to completion and/or lawsuits and/or pending lawsuits against the firm and/or its principals. The County reserves the right to reject any Response if the evidence submitted by, or investigation of, such Contractor fails to satisfy the County and PPRTA that such Contractor is properly qualified to carry out the obligations of the Solicitation and to complete the work contemplated herein. Conditional Responses will not be accepted.

- CONSIGNMENT OF CONTRACT NOT ALLOWED:  Responses will only be considered from firms which are directly engaged in the business of performing the services described in this Solicitation.  Accordingly, no part of this contract can be consigned to another Consultant.

- CONSIGNMENT OF CONTRACT NOT ALLOWED: No part of this contract can be consigned to another Consultant.

- SUBCONTRACTORS OF WORK SHALL BE IDENTIFIED: As part of its Response, the Consultant shall be required to identify any and all subcontractors that will be used in the performance of the contract resulting from this Solicitation. The Consultant shall also identify the capabilities, experience, and portion of the work to be performed by the subcontractor(s). The competency of the subcontractor(s) with respect to skill, responsibility and business standing shall be considered by the County when making the award in the best interest of the County.

- CURRENT LICENSES REQUIRED:  Consultant must obtain and pay for all required licenses, fees, certifications, etc., and will comply with all laws, ordinances, and regulations.  Damages, penalties and/or fines imposed by the County on the Consultant for failure to obtain required licenses, certifications or fees shall be borne by the Consultant. The County may request for the Consultant to provide a current copy of their licenses and certificates prior to award.

- LABOR, MATERIALS AND EQUIPMENT TO BE SUPPLIED BY THE CONSULTANT: Unless otherwise provided in this Solicitation, the Consultant shall furnish all labor, materials, and equipment necessary for satisfactory contract performance. When not specifically identified in this Solicitation, such materials and equipment shall be of a suitable type and grade for the intended purpose.

- ADDITIONAL SERVICES MAY BE PURCHASED DURING CONTRACT PERIOD: Although this Solicitation specifies an exact location where services are to be performed for the County and PPRTA, it is understood and agreed that the County and PPRTA may, during the term of the awarded contract, request additional services for the same or other locations within the proximity of the Project limits from the successful Consultant. This option, if exercised, is the prerogative of the County and PPRTA and shall be honored by the Consultant as a condition of contract award.

- RATES DEFINED:  The rates quoted by the Consultant shall include full compensation for labor, equipment uses, travel time, and any other costs incurred by the Consultant. Hourly rates shall be straight-time for all labor.  Overtime is not allowed under this Solicitation.  Mileage rates shall be consistent with the current Federal rate at all times.

- ACCIDENT PREVENTION: The Consultant shall be required to take safety precautions in an effort to protect persons and property. All Consultants, Consultants and sub-Contractors shall conform to all OSHA, State and County regulations while performing under the terms and conditions of the awarded contract.  Any fines levied by the above-mentioned authorities because of inadequate compliance with these requirements shall be borne solely by the Consultant which is responsible for same.

- DEFICIENCIES IN WORK TO BE CORRECTED BY CONSULTANT: The successful Consultant shall promptly correct all deficiencies in service and/or any work that fails to conform to the Contract Documents. All corrections shall be made immediately after such deficiencies and/or non-conformances are verbally reported to the Consultant by the County's Project Manager. The Consultant shall bear all costs of correcting such rejected work. If the Consultant fails to correct the work within the period specified in this Solicitation, the County reserves the right to place the Consultant in default of its contractual obligations, obtain the services of another Consultant and charge the Consultant for these costs, either through a deduction from the final payment over to the Consultant or through invoicing.

- COMPLETION OF WORK: The Consultant shall adhere to the timeline and milestones provided in its Response in which it will commit to perform the work and/or service. All work shall be performed in accordance with good commercial practice and the timeline and milestones shall be adhered to by the successful Consultant, except in such cases where the timeline will be delayed due to acts of God, strikes, or other causes beyond the control of the Consultant. In these cases, the Consultant shall notify the County of the delays in advance of the original timeline so that a revised timeline can be negotiated. Should the Consultant to whom the contract is awarded fail to complete the work within the timeline as stated in its Response or as subsequently approved, it is hereby agreed and understood that the County reserves the right to cancel the contract with the Consultant and to secure the services of another Consultant to complete the work. If the County exercises this right, the County shall be responsible for reimbursing the Consultant for work which was completed and found acceptable to the County in accordance with the Specifications.   In addition, the County may, at its sole discretion, request payment from the Consultant, through an invoice or credit memo, for any additional costs over and beyond the original price which were incurred by the County as a result of having to secure the services of another Consultant.

- METHOD OF PAYMENT: The successful Consultants shall submit monthly invoices. These invoices shall be submitted to the County's Project Manager.

- DISADVANTAGED BUSINESS ENTERPRISE: The Project is not subject to a DBE goal.

- SALES TAX: The County is exempt from paying State or Local Sales Taxes. Consultants should be aware of CONTRACTOR APPLICATION FOR EXEMPTION CERTIFICATE Pursuant to Statute Section 39- 26.708(1)(a)(XIX) sales tax exemption for construction and building materials. State tax I.D. # 09-803308- 0000, Federal tax I.D. # 84-6000764.

- INDEMNIFICATION: Indemnification – General. The Contractor shall, to the fullest extent permitted by law, defend, indemnify and hold harmless the County, Board of County Commissioners, PPRTA, officials, officers, directors, and employees, from and against all liability, claims, demands, suits, actions or proceedings of any kind that are not the result of or directly related to the performance of professional services, including, without limitation, claims arising from bodily injury, personal injury, sickness, disease, death, property loss or damage, which arise out of or are in any manner connected with this Agreement, including workers' compensation claims, in any way resulting from or arising from the services rendered by the Contractor, its employees, agents or subcontractors, or others for whom the Contractor is legally liable, under this Agreement; provided, however, that the Contractor need not indemnify or save harmless the County Board of County Commissioners, PPRTA, its officers, agents and employees, from damages resulting from the negligence of the County's Board of County Commissioners, PPRTA, officials, officers, directors, agents, and their insurers, and employees. The County and PPRTA cannot and by this Agreement does not agree to indemnify, hold harmless, exonerate, or assume the defense of the Contractor or any other person or entity whatsoever, for any purpose whatsoever.

Indemnification for Professional Services. The Consultant shall, to the fullest extent permitted by law, indemnify and hold harmless the County, Board of County Commissioners, PPRTA, and any of its officials, officers, directors, agents, and their insurers, and employees, from and against damages, liability, losses, costs and expenses, including reasonable attorney’s fees, but only to the extent caused by or arising out of the negligent acts, errors or omissions of the Consultant, its employees, agents or subconsultants, or others for whom the Consultant is legally liable, in the performance of professional services under this Agreement. The Consultant is not obligated to indemnify or hold harmless the County for the negligent acts of the County, Board of County Commissioners, PPRTA, or any of its officials, officers, directors, agents, and employees.

Indemnification – Costs. The Contractor shall, to the extent provided by law, investigate, handle, respond  to, and provide defense for and defend against, any such liability, claims or demands at the sole expense of the Contractor or, at the option of the County and PPRTA, agrees to pay the County and PPRTA or reimburse the County and PPRTA for the defense costs incurred by the County and PPRTA in connection with any such liability, claims or demands. The Contractor shall, to the extent provided by law, bear all other costs and expenses related thereto, including court costs and attorney fees, whether or not any such liability, claims or demands alleged are groundless, false or fraudulent. If it is determined by the final judgment of a court of any competent jurisdiction that such injury, loss or damage was caused in whole or in part by the act, omission or other fault of the County, Board of County Commissioners, PPRTA, officials, officers, directors, agents and employees, the County and PPRTA shall reimburse the Contractor for the portion of the judgment attributable to such act, omission or other fault of the County, Board of County Commissioners, PPRTA, officials, officers, directors, agents and employees.

- FEDERAL FUNDING: ln the event the agreement will use federal funds, Consultant shall comply with the following:

  - Federal Compliance - This Solicitation will be funded, in whole or in part, with an award of federal funds. Consultant shall comply with all applicable federal laws, regulations, and requirements. These include but are not limited to compliance with the following laws and regulations:

- Contract Work Hours and Safety Standards Act (40 U.S.C. 3701-3708). If this Agreement is in excess of $100,000 and involves the employment or mechanics or laborers, Consultant must comply with provisions of 40 U.S.C. 3702, as supplemented by Department of Labor regulations (29 CFR Part 5).

- Rights to Inventions Made Under a Contract or Agreement. If this Agreement is an agreement with a small business firm or nonprofit organization for performance of experimental, developmental, or research, Consultant must comply with the requirements or 37 CFR Part 401, “Rights to Inventions Made by Nonprofit organizations and Small Business Firms Under Government Grants, Contracts and Cooperative Agreements,” and any Implementing regulations issued by the awarding agency.

- Clean Air Act (42 U.S.C. 7401 – 7671q.) and the Federal Water Pollution Control Act (33 U.S.C. 1251-1387). If this Agreement is in excess of $150,000, the Consultant is required to comply with all applicable standards, orders or regulations issued pursuant to the Clean Air Act as amended (42 U.S.C. 7401- 7671q) and the Federal Water Pollution Control Act as amended (33 U.S.C. 1251-1387). Violations must be reported to the Federal awarding agency of the federal funds for this Agreement and the Regional Office of the Environmental Protection Agency (EPA).

- Debarment and Suspension (Executive Orders 12549 and 12689). The County is prohibited from entering into this Agreement with a party listed on the government wide exclusions in the System for Award Management (SAM), in accordance with the OMB guidelines at 2 CFR 180 that implement Executive Orders 12549 (3 CFR part 1986 Comp., p. 189) and 12689 (3 CFR part 1989 Comp., p. 235), “Debarment and Suspension.” SAM Exclusions contains the names of parties debarred, suspended, or otherwise excluded by agencies, as well as parties declared ineligible under statutory or regulatory authority other than Executive Order 12549.

- Byrd Anti-Lobbying Amendment (31 U.S.C. 1352). If this Agreement is for compensation in excess of $100,000, Consultant must file the required certification with the County that it will not and has not used Federal appropriated funds received by the Consultant to pay any person or organization for influencing or attempting to influence an officer or employee or any agency, a member of Congress, officer or employee of Congress, or an employee or a member of Congress in connection with obtaining any Federal contract, grant or any other award covered by 31 U.S.C. 1352. Consultant must also disclose to the County any lobbying with non-Federal funds that takes place in connection with obtaining any Federal award.

- Procurement of Recovered Material (2 CFR CH. II §200.322). Consultant must 1) comply with section 6002 of the Solid Waste Disposal Act, as amended by the Resource Conservation and Recovery Act. The requirements of Section 6002 include procuring only items designated in guidelines of the Environmental Protection Agency (EPA) at 40 CFR part 247 that contain the highest percentage of recovered materials practicable, consistent with maintaining a satisfactory level of competition, where the purchase price of the item exceeds $10,000 or the value of the quantity acquired during the preceding fiscal year exceeded $10,000; 2) procuring solid waste management services in a manner that maximizes energy and resource recovery; and 3) establishing an affirmative procurement program for procurement of recovered materials identified in the EPA guidelines.

- Equal Employment Opportunity. If this Agreement is a construction contract Consultant is required to comply with the equal opportunity clause provided under 41 CFR 60-1.4(b), in accordance with Executive Order 11246, “Equal Employment Opportunity” (30 FR 12319, 12935, 3 CFR Part, 1964-1965 Comp., p. 339), as amended by Executive Order 11246, “Amending Executive Order 11246 Relating to Equal Employment Opportunity,” and Implementing regulations at 41 CFR part 60, “Office or Federal Contract Compliance Programs, Equal Employment Opportunity, Department of Labor."

- Davis-Bacon Act, as amended (40 U.S.C. 3141-3148). If this Agreement is prime construction contract in excess of $2,000, Consultant is required to comply with the Davis-Bacon Act (40 U.S.C. 3141-3144, and 3146-3148) as supplemented by Department of Labor Regulations (29 CFR Part 5, “Labor Standards Provisions Applicable to Contracts Covering Federally Financed and Assisted Construction”).

- Affirmative Action, it is hereby agreed and understood that Section 60-250.4, Section 60-250.5 and Section 60-741.4 of Title 4 of the United States Code, which addresses Affirmative Action requirements for handicapped workers, is incorporated into this Solicitation by reference.

- FEDERAL REGULATION COMPLIANCE DUE TO THE USE OF FEDERAL DOLLARS:  Since the goods, services, and/or equipment that will be acquired under this Solicitation will be purchased, in part or in whole, with federal dollars, it is hereby agreed and understood that Section 60 250.4, Section 60 250.5 and Section 60 741.4 of Title 4 of the United States Code, which addresses Affirmative Action requirements for handicapped workers, is incorporated into this Solicitation by reference.

- FEDERAL STANDARDS COMPLIANCE: All services to be purchased in conjunction with this Solicitation shall be in accordance with all governmental standards to include, but not be limited to, those issued by the Office of Safety and Health Administration (OSHA), the National Institute of Occupational Safety Hazards (NIOSH), and the National Fire Protection Association (NFPA).

- EQUAL OPPORTUNITY: El Paso County and PPRTA intends and expects that the contracting processes of the  County and its Consultants provide equal opportunity without regard to gender, race, creed, ethnicity, religion, age, sex, national origin, or disability and that its Consultants make available equal opportunities to the extent third parties are engaged to provide goods and services to the County as subcontractors, Consultant's, or otherwise. Accordingly, the Consultant shall not discriminate on any of the foregoing grounds in the performance of the contract and shall make available equal opportunities to the extent third parties are engaged to provide goods and services in connection with performance of the contract (joint ventures are encouraged).The Consultant shall disseminate information regarding all subcontracting opportunities under this contract in a manner reasonably calculated to reach all qualified potential subcontractors who may be interested. The Consultant shall maintain records demonstrating its compliance with this article and shall make such records available to the County upon the County’s request.

- PURCHASE BY OTHER GOVERNMENTAL AGENCIES: Each governmental unit which avails itself of this Solicitation will establish its own contact, place its own orders, issue its own purchase orders, be invoiced there from, and make its own payments and issue its own exemption certifications as required by the Consultant. It is understood and agreed that El Paso County is not a legally binding party to any contractual agreement made between any other governmental unit and the Consultant as a result of this Solicitation.

- CONFIDENTIALITY: Responses to this Solicitation are considered to be working documents while they are under consideration and, as such, are not subject to official bid openings. In consideration of this Invitation for Bids that is cost driven, the only information that will be released is the names of the respondents, the total cost of the bids, and the apparent responsible, responsive Consultant. Only after staff makes an  official recommendation of award and a contract is fully executed will Responses to this Bid be available as public record.

Responses submitted to the County for consideration shall be subject to the Colorado Open Records Law, Section 24-72-201, et seq., C.R.S., after award is made. Any confidential information in the Consultant’s Response shall be identified as such. Should the County receive a request for the release of any information in the Consultant’s Response identified as confidential in accordance with the open records law, the County will notify the Consultant of the request and will exercise best efforts in assisting the Consultant in taking all legally available steps to resist or narrow such request. If, in the opinion of County’s legal counsel, the County is nonetheless compelled to disclose any portion of such information to anyone or else stand liable for contempt or suffer censure or penalty, the County may disclose such information without liability.

- GRATUITIES AND KICKBACKS: It shall be a breach of ethical standards for any person to offer, give, or agree to give any employee or former employee (within six months of termination from County employment), or for any employee or former employee (within six months of termination from County employment) to solicit, demand, accept, or agree to accept from another person, a gratuity or an offer of employment in connection with any decision, approval, disapproval, recommendation, preparation of any part of a program requirement or a purchase request, influencing the content of any specification or procurement standard, rendering of advice, investigation, auditing, or in any other advisory capacity in any proceeding of application, request for ruling, determination, claim or controversy, or other particular matter, pertaining to any program requirement or a contract or subcontract, or to any solicitation or bid therefore.

It shall be a breach of ethical standards for any payment, gratuity, or offer of employment to be made by or on behalf of a subcontractor under a contract to the prime Consultant or higher tier subcontractor or any person associated therewith, as an inducement for the award of a subcontract or order. In the event that any gratuities or kickbacks are offered or tendered to any El Paso County employee, the bid shall be disqualified and shall not be reinstated.

- BUDGET: Budget will not be disclosed.

- LOGOS: The County logo is trademarked and property solely of El Paso County. Consultants do not have

permission to use our logo on any documentation or presentation materials and to do so would be a violation of our trademark. We also prefer your company does not utilize its trademark so as to not  influence an evaluator’s review.

REQUEST FOR PROPOSAL #26-016

GENERAL TERMS AND CONDITIONS

- APPLICABILITY. These General Terms and Conditions apply, but are not limited, to all bids, proposals, qualifications and quotations (hereinafter referred to as “Offers” and/or “Responses”) made to PPRTA Pikes Peak Rural Transit Authority (hereinafter referred to as “PPRTA”), El Paso County (hereinafter referred to as "County") by all prospective suppliers (herein after referred to as "Contractors") in response but not limited to Invitations to Bid, Invitations for Bid, Requests for Proposal, Statements of Qualification, and Requests for Quotation (hereinafter referred to as “Solicitations”).

# CONTENTS OF OFFER

  - General Conditions. Consultants are required to submit their Offers in accordance with the following expressed conditions:

    - Consultants shall make all investigations necessary to thoroughly inform themselves regarding the plant and facilities affected by the delivery of materials and equipment as required the conditions of the Solicitation. No plea of ignorance by the Consultant of conditions that exist or that may hereafter exist as a result of failure to fulfill the requirements of the contract documents will be accepted as the basis for varying the requirements or the compensation to the Consultant.

    - Consultants are advised that all County contracts are subject to all legal requirements contained in County ordinances, the Contracts and Procurement policies and state and federal statutes. When conflicts between the Solicitation and these legal documents occur, the highest authority will prevail.

    - Consultants are required to state exactly what they intend to furnish to the County and PPRTA via this Solicitation and must indicate any variances to the terms, conditions, and specifications of this Solicitation no matter how slight. If variations are not stated in the Consultant’s Offer, it shall be construed that the Consultant’s Offer fully complies with all conditions identified in this Solicitation.

    - El Paso County and PPRTA intends and expects that the contracting processes of the County and its Consultants provide equal opportunity without regard to race, color, religion, sex, national origin, age, disability, or any other characteristic protected by law. Accordingly, the Consultant shall not discriminate on any of the foregoing grounds in the performance of the contract.

    - All Offers and other materials submitted in response to this Solicitation shall become the property of the County and will be a matter of public record. Consultants must identify, in writing, all copyrighted material, trade secrets and/or other proprietary information that it claims are exempt from disclosure under the Open Records Act.

    - Any Consultant claiming an exemption must identify the specific provision of the Open Records Act that provides an exemption from disclosure for each item that the Consultant claims is not subject to disclosure and must submit an additional bound copy of the Response with each exempt item clearly redacted. Any Consultant claiming an  exemption must also state in its Response that the Consultant agrees to defend, indemnify, and hold harmless the County and its officers and employees from any action brought against the County for its refusal to disclose any purportedly exempt material, trade secrets and other proprietary information to any party making a request therefore.

Any Consultant who fails to include an exemption statement along with the additional redacted copy of the Response shall be deemed to have waived any right to an exemption from disclosure as provided by the Open Records Act.

  - Clarification and Modifications in Terms and Conditions

    - Where there appear to be variances or conflicts between the General Terms and Conditions, the Special Terms and Conditions and the specifications outlined in this Solicitation, the specifications then the Special Terms and Conditions will prevail.

    - If any Consultant contemplating submitting an Offer under this Solicitation is in doubt as to the true meaning of the specifications, the Consultant must submit a written request for clarification to the County's Contracts and Procurement Manager or their designee as outlined in the Special Terms and Conditions. The Consultant submitting the request  shall be responsible for ensuring that the request is received by the County’s buyer by the date and time listed in the Schedule of Activities for submitting question(s) or as stated in the Special Terms and Conditions.

Any official interpretation of this Solicitation must be made by the County's Contracts and Procurement Manager or their designee. The County shall not be responsible for interpretations offered by other employees of the County.

The County shall issue a written addendum if substantial changes which impact the submission of Offers are required. Addenda will be posted on the Rocky Mountain E- Purchasing System web site (http://www.rockymountainbidsystem.com) as well as El Paso County web site (http://www.elpasoco.com). Consultants are responsible for either revisiting one of these websites prior to the due date or contacting the Contracts and Procurement Manager or their designee named on the Cover Sheet of this Solicitation to ensure that they have any addenda which may have been issued after the initial download.

The Consultant shall certify its acknowledgment of the addendum by signing the addendum and returning it with its Offer. In the event of conflict with the original contract documents, addenda shall govern all other contract documents to the extent specified. Subsequent addenda shall govern over prior addenda only to the extent specified.

  - Prices Contained in Offer-Discounts, Taxes, Collusion

    - It is hereby understood and agreed that the payment terms shall be net thirty days, effective on the date that PPRTA and the County receives an accurate invoice or accepts the products, whichever is the later date.  Payment is deemed to be made on the date of the mailing of the check.

    - Consultants shall not include federal, state, or local excise or sales taxes in prices offered, as the County is exempt from payment of such taxes. Materials purchased directly by the Consultant in conjunction with this contract will, however, be subject to applicable state and local sales taxes. These taxes shall be borne by the Consultant. Under no circumstances shall Consultant be authorized to use the County’s tax exemption number in acquiring such materials.

    - The Consultant, by affixing its signature to this Solicitation, certifies that its Offer is made without previous understanding, agreement, or connection either with any persons, firms or corporations making an Offer for the same items, services, or with the County and PPRTA. The Consultant also certifies that its Offer is in all respects fair, without outside control, collusion, fraud, or otherwise illegal action. To ensure integrity of the County's public procurement process, all Consultants are hereby placed on notice that any and all Consultant s who falsify the certifications required in conjunction with this section will be prosecuted to the fullest extent of the law.

- PREPARATION AND SUBMISSION OF OFFER

  - Preparation

    - El Paso County and PPRTA will not be responsible for any expenses incurred by any Consultant in preparing and submitting its offer.

    - The Offer must be typed or legibly printed in ink. The use of erasable ink is not permitted. All corrections made by the Consultant must be initialed in blue ink by the authorized agent of the Consultant.

    - Offers must contain, in blue ink, a manual signature of an authorized agent of the Consultant or a verifiable electronic time and date stamped signature in the space provided on the Solicitation Cover Sheet. Typed names as signatures are not allowed. The original Cover Sheet of this Solicitation must be included in all Offers.  If the Consultant’s authorized agent fails to appropriately sign and return the original Cover Sheet of the Solicitation, its Offer shall be invalid and shall not be considered.

    - Prices shall be provided by the Consultant on the Solicitation’s Pricing Bid Form when required in conjunction with the prescribed method of award and shall be for the unit of measure requested. Prices that are not in accordance with the measurements and descriptions requested shall be considered non-responsive and shall not be considered. Where there is a discrepancy between the unit price and the extension of prices, the unit price shall prevail.

    - Alternate Offers will not be considered unless expressly permitted in the Specifications and/or Special Terms and Conditions.

    - The accuracy of the Offer is the sole responsibility of the Consultant. No changes in the Offer shall be allowed after the date and time that the Offers are due.

  - Submission

    - The Offer shall be submitted via the Rocky Mountain E-Purchasing System with the Consultant ’s name, the Solicitation Number, and the Solicitation Title. When required in conjunction with the prescribed method of award, the County's Pricing Bid Form must be used when the Consultant is submitting its Offer. The Consultant shall not alter this form (e.g., add or modify categories for posting prices offered) unless expressly permitted in an addendum duly issued by the County. No other form shall be accepted.

    - Offers submitted via facsimile machines, mail, or email will not be accepted unless expressly permitted in the solicitation.

    - Conditional bid offers will be considered non-responsive and not considered for award.

  - Late Offers. Offers received after the date and time set for the opening will not be authorized to enter into the electronic lockbox and will be deemed as non-responsive.

- MODIFICATION OR WITHDRAWAL OF OFFERS

  - Modifications to Offers. Offers may only be modified in the form of a written notice on company letterhead and must be received prior to the time and date set for the Offers to be opened. Each modification submitted to the County’s Contracts and Procurement Division must have the Consultant’s name and return address and the applicable Solicitation number and title clearly marked and shall be submitted via Rocky Mountain E-Purchasing System. If more than one modification is submitted, the modification bearing the latest date of receipt by the County’s Contracts and Procurement Division will be considered the valid modification.

  - Withdrawal of Offers

    - Offers may be withdrawn prior to the time and date set for the opening. Such requests must be made in writing on company letterhead.

    - In accordance with the Uniform Commercial Code, Offers may not be withdrawn after the time and date set for the opening for a period of ninety calendar days after the opening.  If an Offer is withdrawn by the Consultant during this ninety-day period, the County may, at its option, suspend the Consultant from the bid list and may not accept any Offer from the Consultant for a six-month period following the withdrawal.

- REJECTION OF OFFERS

  - Rejection of Offers. The County and PPRTA may, at its sole and absolute discretion:

    - Reject any and all, or parts of any or all, Offers submitted by prospective Consultants;

    - Re-advertise this Solicitation;

    - Postpone or cancel the process;

    - Waive any irregularities in the Offers received in conjunction with this Solicitation; and/or

    - Determine the criteria and process whereby Offers are awarded.  No damages shall be recoverable by any challenger as a result of these determinations or decisions by the County.

  - Rejection of a Particular Offer. The County may reject an offer under any of the following conditions:

    - The Consultant misstates or conceals any material fact in its Offer;

    - The Consultant’s Offer does not strictly conform to the law or the requirements of the Solicitation;

    - The Offer expressly requires or implies a conditional award that conflicts with the method of award stipulated in the Solicitation’s Special Terms and Conditions and/or specifications;

    - The Offer does not include documents, including, but not limited to, certificates, licenses, and/or samples, which are required for submission with the Offer in conjunction with the Solicitation’s Special Terms and Conditions and/or specifications; or

    - The Offer has not been executed by the Consultant through an authorized signature on the Specification’s Cover Sheet.

  - Elimination from Consideration

    - To ensure fair consideration for all Consultants, the County prohibits communication initiated by a Consultant or on a Consultant ’s behalf regarding the Solicitation to or with any County official or employee during the submission process, except as expressly set forth in this Solicitation. In addition, the County prohibits communications initiated by a Consultant or on a Consultant’s behalf to or with any County official or employee evaluating or considering the solicitation prior to the time an award decision has been made. Prohibited communications initiated by a Consultant shall be grounds for eliminating the offending Consultant from consideration for award.

    - An Offer may not be accepted from, nor any contract be awarded to, any person or firm which is in arrears to the County upon any debt or contract or which is a defaulter as surety or otherwise upon any obligation to the County.

    - An Offer may not be accepted from, nor any contract awarded to, any person or firm which has failed to perform faithfully any previous contract with the County, state, or federal government, for a minimum period of three years after this previous contract was terminated for cause.

- AWARD OF CONTRACT. El Paso County, PPRTA, and the successful Consultant shall execute the Trade Consultant Agreement (see Attachment B) to consummate a contract between the parties. This Solicitation and the Consultant’s Offer shall be attached and incorporated as part of that contract.

- CONTRACTUAL OBLIGATIONS

  - Local, State and Federal Compliance Requirements. Successful Consultants shall be familiar and comply with all local, state, and federal directives, ordinances, rules, orders, and laws applicable to, and affected by, this contract including, but not limited to, Equal Employment Opportunity (EEO) regulations, Occupational Safety and Health Act (OSHA), and Title II of the Americans with Disabilities Act (ADA).

    - Accessibility Indemnification: Consultant shall indemnify, save, and hold harmless the Indemnified Parties, against any and all costs, expenses, claims, damages, liabilities, court awards and other amounts (including attorneys’ fees and related costs) incurred by any of the Indemnified Parties in relation to Consultant’s failure to comply with §§24-85-101, et seq., C.R.S., or the Accessibility Standards for Individuals with a Disability as established by OIT pursuant to Section §24-85-103 (2.5), C.R.S.

    - Accessibility: Consultant shall comply with and the Work Product provided under this Contract shall be in compliance with all applicable provisions of §§24-85-101, et seq., C.R.S., and the Accessibility Standards for Individuals with a Disability, as established by OIT pursuant to Section §24-85-103 (2.5), C.R.S. Consultant shall also comply with all State of Colorado technology standards related to technology accessibility and with Level AA of the most current version of the Web Content Accessibility Guidelines (WCAG), incorporated in the State of Colorado technology standards.

  - Disposition. The Consultant shall not assign, transfer, convey, sublet, or otherwise dispose of this contract, including any or all of its right, title or interest therein, or its power to execute such contract to any person, company, or corporation, without prior written consent of the County.

  - Employees.

    - All employees of the Consultant shall be considered to be, at all times, employees of the Consultant, under its sole direction, and not employees or agents of the County. The County may require the Consultant to remove an employee it deems careless, incompetent, insubordinate or otherwise objectionable, and whose continued employment on County property is not in the best interest of the County. In accordance with the County’s policy regarding the use of tobacco products, no employee of the Consultant shall be permitted to use tobacco products when performing work on County property.

  - Workers’ Compensation Insurance. Each Consultant and subcontractor shall maintain at his own expense until completion of his work and acceptance thereof by the County, Workers’ Compensation Insurance, including occupational disease provisions, covering the obligations of the Consultant or subcontractor in accordance with the provisions of the laws of the State of Colorado. The Consultant shall furnish the County with a certificate giving evidence that he is covered by the Workers’ Compensation Insurance herein required, each certificate specifically stating that such insurance includes occupational disease provisions and provisions preventing cancellation without ten days’ prior notice to the County in writing.

  - Delivery. Prices, quotes, and deliveries are to be FOB destination, freight prepaid, and shall require inside delivery unless otherwise specified in the Solicitation’s Special Terms and Conditions. Title and risk of loss shall pass to the County upon inspection and acceptance by the County at its designated point of delivery, unless otherwise specified in the Special Terms and Conditions. In the event that the Consultant defaults on its contract or the contract is terminated for cause due to performance, the County reserves the right to re-procure the materials or services from the next lowest Consultant or from other sources during the remaining term of the terminated/defaulted contract. Under this arrangement, the County shall charge the Consultant any difference between the Consultant’s price and the price to be paid to the next lowest Consultant, as well as any costs associated with the re-solicitation effort.

  - Material or Service Priced Incorrectly. As part of any award resulting from this process, Consultant(s) will discount all transactions as agreed. In the event the County discovers, through its contract monitoring process or formal audit process, that material or service was priced incorrectly, Consultant(s) agree to promptly refund all overpayments and to pay all reasonable audit expenses incurred as a result of the non-compliance.

- CONTRACT MODIFICATIONS. Terms and conditions may be added, modified, and deleted upon mutual agreement between the County, PPRTA, and the Consultant provided that such terms and conditions remain within the scope and original intent of the Solicitation. Said terms and conditions may include, but are not limited to, additions 8.or deletions of service levels and/or commodities and/or increases or decreases in the time limits for an existing contract. Any and all modifications must be expressed in writing through a Contract Modification Order (CMO) and/or Amendment and executed by authorized agents of the County, PPRTA, and the Consultant prior to the enactment of such modifications.

- TERMINATION OF CONTRACT

  - Failure to perform. The County and PPRTA may, by written notice to the successful Consultant, terminate the contract if the Consultant has been found to have failed to perform its service in a manner satisfactory to the County as per specifications, including delivery as specified. The date of termination shall be stated in the notice. The County shall be the sole judge of non-performance.

  - Reasons other than cause. The County and PPRTA may cancel the contract upon thirty days written notice for reason other than cause. This may include the County's inability to continue with the contract due to the elimination or reduction of funding.

REQUEST FOR PROPOSAL #26-016

CONSULTANT INFORMATION FORM

- CONSULTANT

  - Legal Name of Company

  - Business Name or DBA (if different)

- LOCAL COLORADO ADDRESS (IF APPLICABLE)

  - Street Address

  - City/State/Zip

- ORDER ADDRESS

  - Street Address

  - City/State/Zip

  - Online (website)

- PAYMENT ADDRESS

  - Street Address

  - City/State/Zip

- CONTACT INFORMATION

  - Name/Title

  - Telephone Number:

  - Toll Free Number:

  - Fax Number:

  - Email Address:

- TAXPAYER IDENTIFICATION NUMBER

- OWNERSHIP STATUS (check all that apply)	   Corporation	   Partnership

Governmental Agency	   Sole Proprietorship

Individual	   Other

Non-Profit

- PRIMARY BUSINESS CLASSIFICATION	   Broker	   Retailer

Distributor	   Service Provider

Jobber	   Subcontractor (trades)

Manufacturer	   Wholesaler

Prime Contractor (trades)	   Other

- OFFICERS, OWNERS, PARTNERS	Name/Title

Name/Title

- COMPANY PROFILE

  - Date Firm Was Established

  - Under the Laws of What State

  - Number of Employees

  - Approximate Yearly Sales Volume

- PRIMARY PLACE OF BUSINESS	   Home	   Office/Warehouse

Office Building	   Warehouse

Office Complex	   Other

- STAFF EXPERIENCE (key members of your company’s staff who will be assigned to this project)

  - Name/Position	Year Hired

Years in Present Position	Years of Industry Experience

  - Name/Position	Year Hired

Years in Present Position	Years of Industry Experience

  - Name/Position	Year Hired

Years in Present Position	Years of Industry Experience

  - Name/Position	Year Hired

Years in Present Position	Years of Industry Experience

  - Name/Position	Year Hired

Years in Present Position	Years of Industry Experience

- RELEVANT PROJECTS AND REFERENCES

(customers similar to El Paso County to whom services similar in size and scope have been provided)

  - Project Name	Project Location

Project Scope

Services provided by Bidder

Percentage of work by Bidder	Project Timeline	Contract Amount

Company Name	Contact/Title

Address 	City/State /Zip

Telephone 		Email

  - Project Name	 Project Location

Project Scope

Services provided by Bidder

Percentage of work by Bidder	Project Timeline	Contract Amount

Company Name	Contact/Title

Address	 City/State /Zip

Telephone 		 Email

RELEVANT PROJECTS AND REFERENCES (CONTINUED)

  - Project Name	Project Location

Project Scope

Services provided by Bidder

Percentage of work by Bidder	Project Timeline	Contract Amount

Company Name	 Contact/Title

Address	City/State /Zip

Telephone 		Email

  - Project Name	Project Location

Project Scope

Services provided by Bidder

Percentage of work by Bidder	 Project Timeline	Contract Amount

Company Name	Contact/Title

Address	City/State /Zip

Telephone 		  Email

  - Project Name	Project Location

Project Scope

Services provided by Bidder

Percentage of work by Bidder		Project Timeline	Contract Amount

Company Name	Contact/Title

Address	 City/State /Zip

Telephone 		Email

- BONDING. Is your firm able to obtain bonding up to and including an amount equal to the estimated project cost?

Yes      No

- INSURANCE. Is your firm able to obtain insurance as specified in the Special Terms and Conditions of this RFP?

Yes      No

- PURCHASE ORDERS. Do you accept purchase orders?

Yes      No

- CREDIT CARDS. Do you accept credit cards without charging a fee?

Yes      No

- INFORMATION (if you answer “yes” to any of the following questions, attach a separate page explaining your response clearly labeled with the corresponding question number).

  - In the past five years, has there been any change in ownership of your company?

Yes      No	(if “yes,” attach explanation labeled 18a)

  - In the past five years, has your firm operated under any other name?

Yes      No	(if “yes,” attach explanation labeled 18b)

  - Are any corporate officers, owners or partners currently connected with any other firm in the same line of business?

Yes      No	(if “yes,” attach explanation labeled 18c)

  - In the past five years, has your firm been in bankruptcy?

Yes      No	(if “yes,” attach explanation labeled 18d)

  - In the past five years, has your firm been assessed and paid liquidated damages?

Yes      No	(if “yes,” attach explanation labeled 18e)

  - In the past five years, has your firm, or any firm with which your company’s officers, owners or partners are associated, been barred, disqualified, removed, or otherwise prevented from bidding on, or competing for any government project for any reason?

Yes      No	(if “yes,” attach explanation labeled 18f)

  - In the past five years, has your firm been denied an award of any contract based on a finding by a public agency that your company was not a responsible bidder?

Yes      No	(if “yes,” attach explanation labeled 18g)

  - In the past five years, has any claim against your firm concerning your firm’s work on a project been filed in court or arbitration?

Yes      No	(if “yes,” attach explanation labeled 18h)

  - Has your firm made any claim against a project owner concerning work on a project or payment for a contract and filed that claim in court or arbitration?

Yes      No	(if “yes,” attach explanation labeled 18i)

  - Has your firm, or any of its officers, owners, or partners, ever been found liable in a civil suit or found guilty in a criminal action for making any false claim or material misrepresentation to any public agency or entity?

Yes      No	(if “yes,” attach explanation labeled 18j)

  - Has your firm, or any of its officers, owners, or partners, ever been convicted of a crime involving any federal, state, or local law related to your business dealings?

Yes      No	(if “yes,” attach explanation labeled 18k)

  - Has your firm, or any of its officers, owners, or partners, ever been convicted of a federal or state crime of fraud, theft, or any other act of dishonesty?

Yes      No	(if “yes,” attach explanation labeled 18l)

  - In the past five years, has any surety company made any payments on your firm’s behalf as result of a default, to satisfy any claims made against a performance or payment bond issued on your firm’s behalf?

Yes      No	(if “yes,” attach explanation labeled 18m)

  - Has your firm ever been denied bond coverage by a surety company, or has there ever been a period of time when your firm had no surety bond in place during a project when one was required?

Yes      No	(if “yes,” attach explanation labeled 18n)

  - Have you ever had insurance terminated by a carrier?

Yes      No	(if “yes,” attach explanation labeled 18o)

  - In the past five years, has any insurance carrier, for any form of insurance, refused to renew an insurance policy for your firm?

Yes      No	  (if “yes,” attach explanation labeled 18p)

q	In the past five years, has OSHA cited and assessed penalties against your firm?

Yes      No	(if “yes,” attach explanation labeled 18q)

- Licenses. Does your company have current and valid licenses for the services being requested? Please provide copies.

Yes      No	(if “yes,” attach licenses labeled 18)

- Certification. The undersigned hereby affirms (1) that he/she is a duly authorized agent of the Consultant and (2) that the information submitted in/with this form is true and correct. Any information submitted herein that is later found to be false shall serve as grounds for disqualifying the Consultant ’s Response.

  - Printed Name:

  - Printed Title:

  - Firm Name:

  - Address:

  - City, State, Zip:

  - Telephone:

  - Fax:

  - E-mail:

Authorized Representative’s Signature:

Attach all requested exhibit items to the end of this document and clearly label each exhibit with the corresponding question number.

REQUEST FOR PROPOSAL #26-016

PROPRIETARY / CONFIDENTIAL STATEMENT

‘I/We acknowledge that subsequent to award of this solicitation, all of, or part of this submittal may be released to any person or firm who may request I, as prescribed by the State of Colorado Open Records Act CRS 24-72-201 et seq., as amended, and that:

None of this submittal is considered proprietary and/or confidential

# OR

The portions/pages of this submittal identified below are proprietary and/or confidential for the reasons stated (cite the specific exemptions allowed by the Colorado Open Records Act/Government Code). A clearly identified redacted softcopy of the original Response is required if this section is selected.

Page:	Code:	Reason:

# General reference to Freedom of Information Act (FOIA) or Colorado Open Records Act (CORA) is not sufficient justification. The County has the final discretion in determining whether information is subject to disclosure under CORA.

I/We acknowledge that the above statements may be subject to legal review and challenge.

Signature below indicates that applicant has read all the information provided above and agrees to comply in full. This form is considered as a section of the Request for Proposal 26-016 and therefore, this signed document shall be considered and fully submitted with the original package.

Authorized Representative’s Signature	Date

Printed Name	Title

REQUEST FOR PROPOSAL #26-016

NO BID STATEMENT

El Paso County values your input. Your input assists us in building competitive solicitations and ensuring our solicitations are cutting edge and relevant. Please spend a few minutes to complete this form and return it to the Contracts and Procurement Division.

Please send to:	El Paso County

Matthew Marter, Senior Procurement Specialist

RFP-26-016; Design of the Meridian and Flower Road Intersection Improvements Project

matthewmarter@elpasoco.com

Specifications too “strict” (i.e. – geared toward one brand or manufacturer only, etc.). Please explain.

Specifications are unclear. Please explain.

Other. Please explain in detail.

- We are unable to meet specifications

- Insufficient time to respond to the solicitation

- Our schedule would not permit us to perform within the required time

- We are unable to meet insurance and/or bonding requirements

- We do not offer this product or service

PRINT OR TYPE YOUR INFORMATION

Company Name:	Fax:

Address:	City/State/Zip:

Contact Person:	Title:

Email:	Phone:

Authorized Representative’s Signature:	Date:

Printed Name:	 Title:

Email:	Phone:

REQUEST FOR PROPOSAL #26-016

SUBMISSION FORM

ELECTRONIC SUBMISSION OF OFFERS: El Paso County will only accept electronic bid Responses submitted through the Rocky Mountain E-Purchasing system. A Submittal Log will be posted after the County has had an  opportunity to review and verify the submittals offered to the County.

The original Offer must be received before the due date and time through an electronic package transmitted through the Rocky Mountain E-Purchasing system. The Consultant is responsible for ensuring its Response is posted by the due date and time outlined in the solicitation document.

If the submittal arrives late, it will not be included in the electronic lockbox.

ALL signatures on required documents must be in blue ink or a verifiable electronic time and date stamped signature

# Consultant shall check () to confirm that the following documentation has been submitted:

- Signed Cover Sheet from this Solicitation

- Consultant Information Form

- Proprietary / Confidential Statement

- Signed copies of any addenda issued regarding this Solicitation

- Exhibits 1, 2, 3, and 4

- Work Plan and Schedule

- Pricing Form

- Documentation of Evaluation Criteria

Does your offer comply with all of the terms and conditions of this solicitation and the attached Agreement?

Yes	No	If not, indicate exceptions on Exhibit 1.

Does your offer meet or exceed all of the specifications of this solicitation and the attached Agreement?

Yes	No	If not, indicate exceptions on Exhibit 1.

# Consultant ’s response to the following question will not be considered in awarding this Solicitation.

El Paso County actively participates in purchasing between and among government agencies to combine purchasing power and resources and to obtain lower costs of procurement for quality goods and services. As such, we hereby request that other agencies of government be permitted to avail themselves of any award resulting from this solicitation and purchase any and all items specified herein from the successful Consultant(s) at the contract price(s) established herein. Each agency would establish its own contract, issue its own orders, be invoiced therefrom, make its own payments, and issue its own exemption certificates as required by the Consultant. It is understood and agreed that El Paso County would not be a legally binding party to any contractual agreement made between any other agency and the Consultant as a result of this Solicitation.

# May other units of government avail themselves of this contract and purchase any and all items specified.

Yes	No

REQUEST FOR PROPOSAL #26-016

EXHIBIT 1 – EXCEPTIONS FORM

# EXHIBIT 1: EXCEPTIONS

Print the words "no exceptions"(here)                                                     if there are no exceptions taken to any of the terms, conditions, or specifications of these Response documents or contract.

If there are exceptions taken to any of the terms, conditions, or specifications of the Response document or contract, they must be clearly stated on a separate sheet of paper attached to this sheet and returned with your Response.

Note: All potential Consultants are hereby advised that exceptions taken may be considered during the review of your bid which may affect the final decision made by the County. Consultants stipulating that the County must  use their contract or agreement may be determined non-responsive and their Response determined unacceptable.

Company Name:

Address:

(County, State and Zip Code)

Federal Tax ID#:

PHONE:

FAX:

E-MAIL ADDRESS:

Authorized Signature:                                                       Date:

Printed Name/Title:

REQUEST FOR PROPOSAL #26-016

EXHIBIT 2 – LOBBYING RESTRICTION CERTIFICATION

EXHIBIT 2: RESTRICTIONS ON LOBBYING CERTIFICATION

Pursuant to United States Public Law 101-121, Section 319, the undersigned duly authorized official of the proposer hereby certifies, to the best of her/his knowledge and belief, that:

    - No Federal appropriated funds have paid or will be paid, by or on behalf of the undersigned, to any person for the purpose of influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress, in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment, or modification of any Federal contract, grant, loan, or cooperative agreement.

    - If any funds other than Federal appropriated funds have been paid or will be paid to any person or agency for influencing or attempting to influence an officer or employee of any agency, a Member of Congress,  an officer or employee of Congress, or an employee of a Member of Congress, in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned shall complete and submit a Standard Form-LLL, “Disclosure Form to Report Lobbying”, in accordance with its instructions.

    - The undersigned duly authorized official shall require and ensure that the language of this certification be included in any award documents for subcontracts, grants, loans, and cooperative agreements, and that all subcontractors shall so certify and disclose accordingly.

This Certification is a material representation of fact, upon which reliance was placed when this transaction was made or entered into. The submission of this Certification is a prerequisite for making or entering into this transaction, imposed by Title 31 USC Section 1352. Any proposer (person) who fails to file the required certification shall be subject to civil penalty of not less than ten thousand dollars ($10,000) and not more than one hundred thousand dollars ($100,000) for each such failure to file.

# I DO CERTIFY	I DO NOT CERTIFY

Proposer:

Signature:

Title:

Date:

REQUEST FOR PROPOSAL #26-016

EXHIBIT 3 – NON-COLLUSION AFFIDAVIT

# EXHIBIT 3: NON-COLLUSION AFFIDAVIT

The undersigned duly authorized official of the proposer hereby certifies, to the best of her/his knowledge and belief, that:

- That I am an officer or employee of                                                          (proposing entity) having the authority to sign on behalf of the corporation, and,

- That the prices in the attached Response were arrived at independently by

(proposing entity) without collusion, consultation, communication, or any agreement, for the purpose of   restricting competition as to any matter relating to such prices with any other proposer or with any other competitor regarding an understanding, or planned common course of action with any other Consultant of materials, supplies, equipment, or service described in the RFP designed to limit independent Responses or competition; and

- That unless otherwise required by law, the contents and prices contained in the Response have not been communicated by                                                                              (proposing entity) or its employees or agents to any person not an employee or agent of                                                      (proposing entity), or its surety on any bond furnished with the Response, and will not be communicated to any such person prior to the official opening of the Response; and,

- That I have fully informed myself regarding the accuracy of the statements made in this affidavit.

# I DO CERTIFY	I DO NOT CERTIFY

Proposer:

Signature:

Title:

Date:

REQUEST FOR PROPOSAL #26-016

EXHIBIT 4 – MINIMUM INSURANCE REQUIREMENTS

# EXHIBIT 4: MINIMUM INSURANCE REQUIREMENTS

For this contract, the following provisions for insurance shall apply:

The Consultant agrees to procure and maintain, during the life of this Agreement, a policy, or policies of insurance against all liability, claims, demands and other obligations assumed by the Consultant, pursuant to Attachment A. Such insurance shall be in addition to any other insurance requirements imposed by this Agreement or by law. The Consultant shall not be relieved of any liability, claims, demands or other obligations assumed pursuant to Attachment A, by reason of its failure to procure or maintain, during the life of this Agreement, insurance in sufficient amounts, durations, or types.

The Consultant shall procure and maintain, during the life of this Agreement, for itself and shall ensure that any subcontractors procure and maintain, the minimum insurance coverages listed in Attachment A. Such coverages shall be procured and maintained with forms and insurers acceptable to the County and PPRTA. All coverages shall be continuously maintained to cover all liability, claims, demands and other obligations assumed by the Consultant, pursuant to Attachment A. In the case of a claims-made policy, the necessary retroactive dates and extended reporting periods shall be procured to maintain such continuous coverage. Notwithstanding the foregoing, when the Consultant requires a subcontractor to obtain insurance coverage, the types and minimum limits of this coverage may be different than those required, as stated herein for the Consultant.

- The certificate of insurance provided by the Consultant shall be completed by the Consultant 's insurance agent as evidence that policies providing the required coverages, conditions and minimum limits are in full force and effect and shall be received, reviewed, and approved by The County prior to commencement of the Agreement. No other form of certificate shall be used. The certificate shall identify this Agreement and the coverages afforded under the policies. The certificate of insurance must be on file with the County two (2) weeks prior to commencement of the Agreement. The completed certificate of insurance shall be sent to:

El Paso County and

Board of County Commissioners

Attn: Contracts and Procurement Division 15 East Vermijo Avenue

Colorado Springs, Colorado 80903

- It is the affirmative obligation of the Consultant to notify the El Paso County's Contracts and Procurement Division, as provided in this Agreement, including e-mailing (PURCOI@elpasoco.com) a copy of the notice to the Contracts and Procurement Division, within two (2) business days of the cancellation or substantive change to any insurance policy required under this Agreement, and failure to do so shall constitute a breach of this Agreement.

- Failure on the part of the Contractor to procure or maintain policies providing the required coverages, conditions and minimum limits shall constitute a material breach of contract upon which the County and PPRTA may immediately terminate this Agreement or, at its discretion, the County and PPRTA may procure or renew any such policy or any extended reporting period thereto and may pay any and all premiums in connection therewith, and all monies so paid by the County and PPRTA shall be repaid by Contractor to the County and PPRTA upon demand, or the County and PPRTA may offset the cost of the premiums against any monies due to Contractor from the County and PPRTA.

- The County and PPRTA reserves the right to request and receive a certified copy of any policy and any endorsement thereto should such a need arise to offset a court proceeding.

- The parties hereto understand and agree that the County, its officers and employees, are relying on and do not waive or intend to waive by any provision of this Agreement the monetary limitations (presently Four Hundred Twenty-Four Thousand Dollars ($424,000) per person, and One Million One Hundred Ninety-Five Thousand Dollars ($1,195,000) per occurrence), which amounts shall be adjusted by an amount reflecting the percentage change over a four-year period in the United States Department of Labor, Bureau of Labor Statistics, Consumer Price Index for Denver-Boulder-Greeley, All Items, All Urban Consumers, or its successor index, or any other rights, immunities and protections provided by the Colorado Governmental Immunity Act, C.R.S. § 24-10-101, et seq., as from time to time amended, or otherwise available to the County, its officers or employees.

El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners must be included on the General Liability insurance as an additional insured. Certificates of Insurance must be submitted before commencing work and provide 30 days’ notice prior to any cancellation.

It shall be the responsibility of the Consultant to ensure that all subcontractors carry insurance of not less than those coverages and limits specified herein. Proper evidence of this compliance must be forwarded to El Paso County's Contracts and Procurement Division prior to the inception of any work by subcontractor.

The undersigned certifies and agrees to procure and maintain the insurance requirements indicated above and on Attachment A throughout the contract Period of Performance.

(Name of Company)

(Signature)	(Date)

# ATTACHMENT A

INSURANCE CHECKLIST

SOLICITATION NUMBER: RFP-26-016

TITLE OF SOLICITATION: Design of the Meridian and Flower Road Intersection Improvements Project

Insurance items checked below have been identified as necessary requirements for this Consultant per the desired scope of work.

EL PASO COUNTY, PIKES PEAK RURAL TRANSPORTATION AUTHORITY, AND BOARD OF COUNTY COMMISSIONERS SHALL BE NAMED AS ADDITIONAL INSURED ON ALL RELEVANT POLICIES.

| Insurance Item: | Required | Waived |
| --- | --- | --- |
| Contractor shall obtain and maintain, and ensure that each Subcontractor shall obtain and maintain, insurance as specified below at all times during the term of this Contract. All insurance policies required by this Contract shall be issued by insurance companies as approved by the County and PPRTA. | X |  |
| Workers’ Compensation: Workers’ compensation insurance as required by state statute, and employers’ liability insurance covering all Contractor or Subcontractor employees acting within the course and scope of their employment. Employers’ Liability with minimum limits as follows: $1,000,000 bodily injury for each accident, $1,000,000 each employee for disease, $1,000,000 disease aggregate. Coverage shall include a Waiver of Subrogation in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. | X |  |
| Commercial General Liability: Commercial general liability insurance covering premises operations, fire damage, independent contractors, products and completed operations, blanket contractual liability, personal injury, and advertising liability with minimum limits as follows: $1,000,000 each occurrence; $2,000,000 general aggregate; $2,000,000 products and completed operations aggregate; and $50,000 damage to premises rented to you – any one premises. Coverage shall include Additional Insured Endorsement and a Waiver of Subrogation in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. | X |  |
| Automobile Liability: Automobile liability insurance covering any auto (including owned, hired, and non-owned autos) with a minimum limit of $1,000,000 each accident combined single limit. Coverage shall include Additional Insured Endorsement and a Waiver of Subrogation in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. | X |  |
| Subrogation Waiver: (When required) Contractor in relation to this contract shall include clauses stating that each carrier shall waive all rights of recovery under subrogation or otherwise against the Board of County Commissioners, El Paso County, Pikes Peak Rural Transportation Authority, its agencies, institutions, organizations, officers, agents, employees, and volunteers. | X |  |
| Garagekeepers Coverage: Garagekeepers coverage for loss to vehicles in the Contractors custody for servicing or storage with a minimum limit of $500,000 for each loss. Coverage shall list El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners as a loss payee. |  | X |
| Umbrella Liability Insurance: Commercial Umbrella/Excess Liability Insurance for bodily injury and property damage liability must sit over Contractor’s primary Employer’s Liability, Commercial General Liability and Commercial Automobile Liability with limits of: $1,000,000 each occurrence and aggregate. Higher or Lower limits may be required or determined acceptable at the sole discretion of County. Coverage shall include Additional Insured Endorsement and a Waiver of Subrogation in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. | X |  |
| Cyber Liability: If Contractor’s scope of work will include access to Protected Information/Confidential Information, such as PII, PHI, PCI, Tax Information, and CJI, Contractor shall maintain Cyber/ Network Security and Privacy Liability Insurance in an amount of not less than $1,000,000 each occurrence; and $2,000,000 general aggregate to cover civil, regulatory and statutory damages, contractual damage, as well as data breach management exposure, and any loss of income or extra expense as a result of actual or alleged breach, violation or infringement of right to privacy, consumer data protection law, confidentiality or other legal protection for personal information, as well as confidential information of County and PPRTA. |  | X |
| Pollution Liability: If Contractor’s scope of work includes any pollution liability exposure, Contractor must provide and maintain a separate Pollution Liability Insurance policy. Such insurance shall include coverage for the Hold-Harmless or Indemnification Clause contained in this Agreement. Coverage shall include a limit of liability no less than $1,000,000 each occurrence and aggregate. Coverage shall include Additional Insured Endorsement in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. |  | X |
| Malpractice Insurance: Professionals to include: physicians, nurses, psychologists, etc. If Contractor’s scope of work includes the performance of professional services providing healthcare or mental health services, Contractor shall provide and maintain, for the statute of repose, Malpractice insurance covering any damages or allegations of negligence, error, or omissions in performance of the professional services with minimum limits as follows: $1,000,000 each claim; and $2,000,000 general aggregate. Coverage shall include Additional Insured Endorsement and a Waiver of Subrogation in favor of El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners. |  | X |
| Professional Liability Insurance: Professionals to include: Architects, Engineers, Construction Managers, IT Consultants/Programmers, Insurance Brokers, Accountants, Real Estate Agents, Etc.. If Contractor’s scope of work includes the performance of professional services, Contractor shall provide and maintain, for the statute of repose, Professional liability insurance covering any damages caused by errors, omissions, or negligent professional act in performance of the professional services with minimum limits as follows: $1,000,000 each claim; and $2,000,000 general aggregate. | X |  |
| Crime Insurance: If Contractor’s scope of work includes Contractor or Contractor’s employees’ involvement with money or securities of County, Contractor shall provide and maintain Commercial Crime coverage for a loss arising out of or in connection with any fraudulent or dishonest act committed by employees of the Contractor, in an amount of not less than $1,000,000 single limit. Commercial Crime Coverage shall include third party liability coverage. Coverage shall list El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners as a loss payee. |  | X |
| Builders Risk: The Contractor shall purchase and maintain All Risk Builder's Risk insurance upon the entire Project to One Hundred Percent (100%) of the insurable value thereof for the benefit of the Owner and the Contractor. Such insurance shall include any and all direct damage to all structures under construction (including temporary structures) and all materials, supplies, machinery, and equipment at the work site which are or will be incorporated in the work, which is caused by hazards such as but not limited to, the hazards of fire, lightning, wind, earthquake, flood, vandalism, malicious mischief, and other hazards included in a standard Extended Coverage Endorsement. Coverage shall list El Paso County, Pikes Peak Rural Transportation Authority, and Board of County Commissioners as a loss payee. |  | X |

REQUEST FOR PROPOSAL #26-016

ATTACHMENT B – SAMPLE PROFESSIONAL SERVICES AGREEMENT

The El Paso County and PPRTA Sample Professional Services Agreement is included in this solicitation for information and reference purposes only.

It is the responsibility of the Contractor to provide any exceptions to this Solicitation and/or El Paso County and PPRTA Sample Professional Services Agreement with its response for evaluation by El Paso County. It is the responsibility of the Consultant to provide the Solicitation and El Paso County and PPRTA Sample Professional Services Agreement to their Legal Counsel for review and notation of any exceptions prior to submitting a bid.

Following the determination of award, El Paso County, PPRTA, and the successful Contractor will execute this document to consummate a contract between the parties. The Solicitation and the Contractor’s Offer will be attached and incorporated as part of the contract.

# REMAINDER OF PAGE LEFT INTENTIONALLY BLANK